## Inputs
Estimation Inputs
Delivery Model | Hybrid Service Delivery
Journey | 1 Journey
Deployment | 1 Deployment
Default Complexity | Medium
Readiness/Maturity Multiplier
Readiness Level (calculated)

## Lookups - JourneyDeployment
Journey options |  | Deployment options |  | Complexity | Delivery owner | Role mapping (WBS → standard rate role)
Journey | Multiplier | Deployment | Multiplier | Option | Option | WBS Role | Standard Role
1 Journey | 1 | 1 Deployment | 1 | Low | Knapsack | CX Partner | CX Partner
2–3 Journeys | 1.5 | 2 Deployments | 1.4 | Medium | Client/SCE | Project Manager | Project Manager
4–6 Journeys | 2 | 3–5 Deployments | 2 | High |  | Engineer | Solution Analyst
7+ Journeys | 3 | 6+ Deployments | 2.8 |  |  | SME | SME
[6 empty] | Design Lead | Executive

## Rates
Standard Role | Provider | Rate ($/hr) | Source | Key
CX Partner | Knapsack | 600 | Knapsack bill rate | CX Partner¦Knapsack
Senior Solution Analyst | Knapsack | 550 | Knapsack bill rate | Senior Solution Analyst¦Knapsack
Solution Analyst | Knapsack | 400 | Knapsack bill rate | Solution Analyst¦Knapsack
Project Manager | Knapsack | 400 | Knapsack bill rate | Project Manager¦Knapsack
SME | Knapsack | 750 | Knapsack bill rate | SME¦Knapsack
Executive | Knapsack | 825 | Knapsack bill rate | Executive¦Knapsack
CX Partner | Client/SCE | 140 | Default CSE rate (edit) | CX Partner¦Client/SCE
Senior Solution Analyst | Client/SCE | 140 | Default CSE rate (edit) | Senior Solution Analyst¦Client/SCE
Solution Analyst | Client/SCE | 140 | Default CSE rate (edit) | Solution Analyst¦Client/SCE
Project Manager | Client/SCE | 140 | Default CSE rate (edit) | Project Manager¦Client/SCE
SME | Client/SCE | 140 | Default CSE rate (edit) | SME¦Client/SCE
Executive | Client/SCE | 140 | Default CSE rate (edit) | Executive¦Client/SCE

## Readiness & Maturity
Readiness & Maturity (PCRI-driven)
PCRI is calculated on the 'PCRI Assessment' tab. Outputs below drive estimation multipliers and WBS prescription.
PCRI Score | Archetype | Default Multiplier | Notes
Archetype | Builder | 1.5 | More foundation + enablement
Foundation (effective) | Adopter | 1.2 | Enablement sprint + adoption
AI Readiness (effective) | Optimizer | 1 | Standard delivery
Governance (effective) | Transformer | 0.9 | Less enablement; faster execution
Delivery (effective)
Culture (effective)
AI Gate Applied?
Delivery Gate Applied?
Multiplier mapping (edit if needed) | Archetype → Multiplier Mapping
Readiness level (used by Inputs) | Edit the multipliers in column E to calibrate by archetype.
Multiplier

## Activity Settings
Phase | Activity / Milestone | # Subtasks | Complexity (input) | Base Hours (lookup) | Readiness Mult | Journey Mult | Deployment Mult | Adjusted Total Hours | Adjusted Hours / Subtask | Owner Override (Hybrid) | Owner Used | Activity Key | PCRI Mult (include/prescribe)
Implementation + Onboarding | Stakeholder Alignment Workshops | 5 | [7 empty] | Knapsack
Implementation + Onboarding | Program management and coordination | 5 | [7 empty] | Knapsack
Implementation + Onboarding | Communication Launch Plan | 5 | [7 empty] | Knapsack
Implementation + Onboarding | Preparation | 5 | [7 empty] | Knapsack
Implementation + Onboarding | Local install support | 5 | [7 empty] | Knapsack
Implementation + Onboarding | Component rendering | 5 | [7 empty] | Knapsack
Implementation + Onboarding | SME support for rendering | 5 | [7 empty] | Knapsack
Implementation + Onboarding | Deployment support | 5 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Program management and Steering Committee coordination | 5 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Facilitating and supporting deliverables | 5 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Change Readiness Assessment | 5 | [7 empty] | Knapsack
Scaled Rollout and Adoption | FDE led Implementation + Architecture + Governance | 4 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Stakeholder Interviews/Workshops | 5 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Pilot Enablement & Feedback Loop | 5 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Role-Based Training Enablement | 5 | [7 empty] | Knapsack
Scaled Rollout and Adoption | SME support for Deployment/DevOps | 4 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Cloud authoring setup and testing | 4 | [7 empty] | Knapsack
Scaled Rollout and Adoption | SSO setup and testing | 4 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Training - Eng / UX / Partners | 4 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Workflow Diagrams | 4 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Content planning and integration | 4 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Advanced Training - Partners + Contribution | 4 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Phase Gate Strategic Recommendations + Documentation | 4 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Pre-Cutover Readiness Review | 4 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Data & Configuration Freeze | 4 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Final UAT & Stakeholder Acceptance | 4 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Change Impact Analysis | 4 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Adoption Acceleration Campaign | 4 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Partner Enablement & Recognition | 4 | [7 empty] | Knapsack
Optimization and Continued Support | Transition support | 4 | [7 empty] | Knapsack
Optimization and Continued Support | Cutover Execution | 4 | [7 empty] | Knapsack
Optimization and Continued Support | Go-Live Communication Launch | 4 | [7 empty] | Knapsack
Optimization and Continued Support | Hypercare Phase (Post-Go-Live Support) | 4 | [7 empty] | Knapsack
Optimization and Continued Support | Post-Implementation Review | 4 | [7 empty] | Knapsack
Optimization and Continued Support | Transition to Steady-State Operations | 4 | [7 empty] | Knapsack
Optimization and Continued Support | Continuous Improvement Framework | 4 | [7 empty] | Knapsack
Optimization and Continued Support | Strategic Partnership Review | 4 | [7 empty] | Knapsack
Optimization and Continued Support | Case Study Development | 4 | [7 empty] | Knapsack
Implementation + Onboarding | Design System Charter & Reference Architecture | 5 | [7 empty] | Knapsack
Implementation + Onboarding | Foundations & Token Taxonomy | 6 | [7 empty] | Knapsack
Implementation + Onboarding | Token Pipeline Build & Theming Strategy | 6 | [7 empty] | Knapsack
Implementation + Onboarding | Component Inventory & Prioritization | 5 | [7 empty] | Knapsack
Implementation + Onboarding | Component API Standards & Templates | 5 | [7 empty] | Knapsack
Implementation + Onboarding | Code Connect Strategy & Configuration | 6 | [7 empty] | Knapsack
Implementation + Onboarding | Documentation IA & Templates (Design System Docs) | 5 | [7 empty] | Knapsack
Implementation + Onboarding | Quality Gates Setup (A11y, Visual, Performance, Security) | 6 | [7 empty] | Knapsack
Implementation + Onboarding | Release Engineering & Package Strategy | 6 | [7 empty] | Knapsack
Implementation + Onboarding | AI Contextual Capabilities – Context Model & Knowledge Base | 7 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Component Library MVP Build (Core Set) | 7 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Code Connect Coverage Expansion & Drift Remediation | 6 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Docs Launch + Recipes & Migration Guides | 5 | [7 empty] | Knapsack
Scaled Rollout and Adoption | Partner Contribution Pathway & Certification | 6 | [7 empty] | Knapsack
Scaled Rollout and Adoption | AI Contextual Capabilities – Workflow Integrations | 6 | [7 empty] | Knapsack
Scaled Rollout and Adoption | AI Contextual Capabilities – Evaluation Harness + Telemetry | 6 | [7 empty] | Knapsack
Optimization and Continued Support | Continuous Quality & Accessibility Automation | 5 | [7 empty] | Knapsack
Optimization and Continued Support | Release Cadence, Deprecations & Migrations | 5 | [7 empty] | Knapsack
Optimization and Continued Support | Adoption Analytics & Reporting (Design↔Code) | 4 | [7 empty] | Knapsack
Optimization and Continued Support | AI Contextual Capabilities – Guardrails, Governance & Iteration | 6 | [7 empty] | Knapsack
Optimization and Continued Support | AI Contextual Capabilities – Feedback Loop + Knowledge Refresh | 4 | [7 empty] | Knapsack

## WBS - Estimate
Phase | Activity / Milestone | Subtask | Deliverable | Deliverable Description | Knapsack Role Description | Accountable Party | Role | Timeline (Weeks) | Standard Role | Activity Key | Hours / Subtask (adjusted) | Owner Used | Rate ($/hr) | Est. Cost
Implementation + Onboarding | Stakeholder Alignment Workshops | Identify executive and operational stakeholders |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 1–2
Implementation + Onboarding | Stakeholder Alignment Workshops | Conduct alignment workshops and capture insights |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 1–2
Implementation + Onboarding | Stakeholder Alignment Workshops | Develop stakeholder map and influence matrix |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 1–2
Implementation + Onboarding | Stakeholder Alignment Workshops | Draft communication strategy and feedback cadence |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 1–2
Implementation + Onboarding | Stakeholder Alignment Workshops | Review and sign off communication plan with Steering Committee | Stakeholder Map, Communication Strategy Draft | Ensure executive and stakeholder alignment before kickoff. | CX Partner - Change Management SME | Adobe | CX Partner | 1–2
Implementation + Onboarding | Program management and coordination | Establish governance tracker and cadence calendar |  |  | Project Manager | Knapsack | Project Manager | 1–20
Implementation + Onboarding | Program management and coordination | Schedule weekly syncs and milestone reviews |  |  | Project Manager | Knapsack | Project Manager | 1–20
Implementation + Onboarding | Program management and coordination | Maintain RAID log |  |  | Project Manager | Knapsack | Project Manager | 1–20
Implementation + Onboarding | Program management and coordination | Prepare Phase 1 exit and readiness report |  |  | Project Manager | Knapsack | Project Manager | 1–20
Implementation + Onboarding | Program management and coordination | Present status updates to Adobe Steering Committee | Project Governance Tracker, Phase 1 Exit Report | Program coordination, kickoff, and phase review oversight. | Project Manager | Knapsack | Project Manager | 1–20
Implementation + Onboarding | Communication Launch Plan | Create internal messaging and visual identity kit |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 3–6
Implementation + Onboarding | Communication Launch Plan | Develop launch materials (FAQ, deck, announcement) |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 3–6
Implementation + Onboarding | Communication Launch Plan | Align with design ops for internal brand tone and channels |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 3–6
Implementation + Onboarding | Communication Launch Plan | Distribute campaign via Adobe internal comms |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 3–6
Implementation + Onboarding | Communication Launch Plan | Gather feedback and refine messaging | Internal Communication Plan, Branding Package | Launch program messaging, goals, and brand identity across teams. | CX Partner - Change Management SME | Adobe | CX Partner | 3–6
Implementation + Onboarding | Preparation | Conduct environment readiness check |  |  | Project Manager | Knapsack | Project Manager | 7–10
Implementation + Onboarding | Preparation | Validate API and endpoint configuration |  |  | Project Manager | Knapsack | Project Manager | 7–10
Implementation + Onboarding | Preparation | Verify authentication and permissions access |  |  | Project Manager | Knapsack | Project Manager | 7–10
Implementation + Onboarding | Preparation | Confirm hosting and network compliance |  |  | Project Manager | Knapsack | Project Manager | 7–10
Implementation + Onboarding | Preparation | Document results in Technical Readiness Checklist | Technical Readiness Checklist | Verify infrastructure readiness, environment setup, and permissions. | Project Manager | Knapsack | Project Manager | 7–10
Implementation + Onboarding | Local install support | Provide installation guide and validation checklist |  |  | Senior Solutions Engineer | Knapsack | Engineer | 7–10
Implementation + Onboarding | Local install support | Support local environment configuration |  |  | Senior Solutions Engineer | Knapsack | Engineer | 7–10
Implementation + Onboarding | Local install support | Troubleshoot integration issues |  |  | Senior Solutions Engineer | Knapsack | Engineer | 7–10
Implementation + Onboarding | Local install support | Validate connectivity with IPE components |  |  | Senior Solutions Engineer | Knapsack | Engineer | 7–10
Implementation + Onboarding | Local install support | Log and close install-related tickets | Installation Validation Report | Validate local environment setup for Knapsack and IPE components. | Senior Solutions Engineer | Knapsack | Engineer | 7–10
Implementation + Onboarding | Component rendering | Validate core Spectrum components rendering |  |  | Senior Solutions Engineer | Knapsack | Engineer | 7–10
Implementation + Onboarding | Component rendering | Conduct visual and functional QA across environments |  |  | Senior Solutions Engineer | Knapsack | Engineer | 7–10
Implementation + Onboarding | Component rendering | Compare results with baseline expectations |  |  | Senior Solutions Engineer | Knapsack | Engineer | 7–10
Implementation + Onboarding | Component rendering | Document rendering test summary report |  |  | Senior Solutions Engineer | Knapsack | Engineer | 7–10
Implementation + Onboarding | Component rendering | Submit remediation recommendations | Rendering QA Report | Validate successful rendering of Spectrum components across environments. | Senior Solutions Engineer | Knapsack | Engineer | 7–10
Implementation + Onboarding | SME support for rendering | Review component architecture and consistency |  |  | Subject Matter Expert | Knapsack | SME | 7–10
Implementation + Onboarding | SME support for rendering | Audit rendering pipeline and dependency mapping |  |  | Subject Matter Expert | Knapsack | SME | 7–10
Implementation + Onboarding | SME support for rendering | Validate accessibility compliance |  |  | Subject Matter Expert | Knapsack | SME | 7–10
Implementation + Onboarding | SME support for rendering | Provide expert input to engineering team |  |  | Subject Matter Expert | Knapsack | SME | 7–10
Implementation + Onboarding | SME support for rendering | Approve Architecture Validation Log | Architecture Validation Log | SME oversight of rendering logic and architectural consistency. | Subject Matter Expert | Knapsack | SME | 7–10
Implementation + Onboarding | Deployment support | Define deployment workflow and CI/CD configuration |  |  | Senior Solutions Engineer | Knapsack | Engineer | 15–20
Implementation + Onboarding | Deployment support | Create rollback and versioning process |  |  | Senior Solutions Engineer | Knapsack | Engineer | 15–20
Implementation + Onboarding | Deployment support | Run initial deployment test |  |  | Senior Solutions Engineer | Knapsack | Engineer | 15–20
Implementation + Onboarding | Deployment support | Record metrics against success criteria |  |  | Senior Solutions Engineer | Knapsack | Engineer | 15–20
Implementation + Onboarding | Deployment support | Approve Deployment Plan and Success Metrics | Deployment Plan + Success Metrics | Plan and validate deployment pipelines with measurable success criteria. | Senior Solutions Engineer | Knapsack | Engineer | 15–20
Scaled Rollout and Adoption | Program management and Steering Committee coordination | Conduct bi-weekly stand-ups with stakeholders |  |  | Project Manager | Adobe | Project Manager | 21–32
Scaled Rollout and Adoption | Program management and Steering Committee coordination | Prepare monthly summary reports |  |  | Project Manager | Adobe | Project Manager | 21–32
Scaled Rollout and Adoption | Program management and Steering Committee coordination | Track progress against milestones |  |  | Project Manager | Adobe | Project Manager | 21–32
Scaled Rollout and Adoption | Program management and Steering Committee coordination | Facilitate phase-gate review sessions |  |  | Project Manager | Adobe | Project Manager | 21–32
Scaled Rollout and Adoption | Program management and Steering Committee coordination | Update Governance Toolkit documents | Governance Toolkit + Monthly Summary Reports | Kickoff, bi-weekly stand-ups, monthly reports, phase gate reviews. | Project Manager | Adobe | Project Manager | 21–32
Scaled Rollout and Adoption | Facilitating and supporting deliverables | Collect adoption and engagement metrics |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 21–32
Scaled Rollout and Adoption | Facilitating and supporting deliverables | Populate dashboard with KPIs |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 21–32
Scaled Rollout and Adoption | Facilitating and supporting deliverables | Review metrics with CX Partner and PM |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 21–32
Scaled Rollout and Adoption | Facilitating and supporting deliverables | Recommend improvements for lagging metrics |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 21–32
Scaled Rollout and Adoption | Facilitating and supporting deliverables | Share monthly change-management insights | Change Management Dashboard | Track adoption metrics, stakeholder engagement, and training completion. | CX Partner - Change Management SME | Adobe | CX Partner | 21–32
Scaled Rollout and Adoption | Change Readiness Assessment | Draft readiness survey and baseline questions |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 21–24
Scaled Rollout and Adoption | Change Readiness Assessment | Conduct assessment sessions |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 21–24
Scaled Rollout and Adoption | Change Readiness Assessment | Analyze cultural and operational preparedness |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 21–24
Scaled Rollout and Adoption | Change Readiness Assessment | Summarize results in Readiness Index |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 21–24
Scaled Rollout and Adoption | Change Readiness Assessment | Present findings to leadership | Readiness Survey, Baseline Adoption Index | Assess cultural, technical, and operational readiness prior to implementation. | CX Partner - Change Management SME | Adobe | CX Partner | 21–24
Scaled Rollout and Adoption | FDE led Implementation + Architecture + Governance | Define system-of-systems architecture |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | FDE led Implementation + Architecture + Governance | Document governance model and accessibility plan |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | FDE led Implementation + Architecture + Governance | Review architecture with engineering leads |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | FDE led Implementation + Architecture + Governance | Finalize and publish architecture document | System of Systems Architecture Document | Define architecture, component contribution model, accessibility, governance framework. | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | Stakeholder Interviews/Workshops | Schedule interviews across departments |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | Stakeholder Interviews/Workshops | Capture key challenges and opportunities |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | Stakeholder Interviews/Workshops | Consolidate findings into themes |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | Stakeholder Interviews/Workshops | Draft recommendations report |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | Stakeholder Interviews/Workshops | Present Strategic Readout | Strategic Readout and Recommendations | Collect stakeholder inputs and align roadmap. | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | Pilot Enablement & Feedback Loop | Identify pilot groups and roles |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 23–26
Scaled Rollout and Adoption | Pilot Enablement & Feedback Loop | Conduct onboarding sessions |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 23–26
Scaled Rollout and Adoption | Pilot Enablement & Feedback Loop | Gather qualitative feedback |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 23–26
Scaled Rollout and Adoption | Pilot Enablement & Feedback Loop | Build sentiment dashboard |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 23–26
Scaled Rollout and Adoption | Pilot Enablement & Feedback Loop | Review results and refine approach | Pilot Feedback Summary, Sentiment Dashboard | Gather early adopter feedback and adjust onboarding approach. | CX Partner - Change Management SME | Adobe | CX Partner | 23–26
Scaled Rollout and Adoption | Role-Based Training Enablement | Segment audience (UX, Eng, Partners) |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 25–28
Scaled Rollout and Adoption | Role-Based Training Enablement | Develop persona-specific materials |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 25–28
Scaled Rollout and Adoption | Role-Based Training Enablement | Host training sessions |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 25–28
Scaled Rollout and Adoption | Role-Based Training Enablement | Assess comprehension via surveys |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 25–28
Scaled Rollout and Adoption | Role-Based Training Enablement | Update modules as needed | Persona-Based Training Modules (UX, Eng, Partner) | Deliver tailored enablement by persona to improve comprehension and adoption. | CX Partner - Change Management SME | Adobe | CX Partner | 25–28
Scaled Rollout and Adoption | SME support for Deployment/DevOps | Review CI/CD pipelines for readiness |  |  | Subject Matter Expert | Knapsack | SME | 21–26
Scaled Rollout and Adoption | SME support for Deployment/DevOps | Validate automation scripts |  |  | Subject Matter Expert | Knapsack | SME | 21–26
Scaled Rollout and Adoption | SME support for Deployment/DevOps | Confirm test coverage completeness |  |  | Subject Matter Expert | Knapsack | SME | 21–26
Scaled Rollout and Adoption | SME support for Deployment/DevOps | Document readiness report | DevOps Readiness | Validate CI/CD, cloud authoring, and deployment automation readiness. | Subject Matter Expert | Knapsack | SME | 21–26
Scaled Rollout and Adoption | Cloud authoring setup and testing | Configure cloud authoring environment |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Cloud authoring setup and testing | Migrate initial content set |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Cloud authoring setup and testing | Validate performance and permissions |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Cloud authoring setup and testing | Document validation results | Cloud Authoring Validation | Setup and validate authoring in cloud environments. | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | SSO setup and testing | Integrate with Adobe’s identity provider |  |  | Subject Matter Expert | Knapsack | SME | 25–28
Scaled Rollout and Adoption | SSO setup and testing | Test authentication flow and failover |  |  | Subject Matter Expert | Knapsack | SME | 25–28
Scaled Rollout and Adoption | SSO setup and testing | Validate group mapping |  |  | Subject Matter Expert | Knapsack | SME | 25–28
Scaled Rollout and Adoption | SSO setup and testing | Document SSO integration results | SSO Integration Checklist | Configure and test single sign-on with enterprise identity provider. | Subject Matter Expert | Knapsack | SME | 25–28
Scaled Rollout and Adoption | Training - Eng / UX / Partners | Develop unified curriculum |  |  | Senior Solutions Engineer | Adobe | Engineer | 29–32
Scaled Rollout and Adoption | Training - Eng / UX / Partners | Schedule and deliver training |  |  | Senior Solutions Engineer | Adobe | Engineer | 29–32
Scaled Rollout and Adoption | Training - Eng / UX / Partners | Track attendance and feedback |  |  | Senior Solutions Engineer | Adobe | Engineer | 29–32
Scaled Rollout and Adoption | Training - Eng / UX / Partners | Refine enablement materials | Unified Enablement Curriculum | Integrated training for engineering, UX, and partner audiences. | Senior Solutions Engineer | Adobe | Engineer | 29–32
Scaled Rollout and Adoption | Workflow Diagrams | Document self-service and contribution workflows |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | Workflow Diagrams | Create FigJam diagrams |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | Workflow Diagrams | Review with design ops and engineering |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | Workflow Diagrams | Publish workflow package | Workflow Documentation (FigJam, Token Studio, Contribution Workflows) | Map self-service contribution and implementation workflows. | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | Content planning and integration | Map documentation inventory |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Content planning and integration | Create cross-platform implementation guides |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Content planning and integration | Validate completeness and consistency |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Content planning and integration | Publish documentation set | Multi-platform Implementation Guides | Documentation for web, React, iOS, Android implementations. | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Advanced Training - Partners + Contribution | Identify advanced partner cohort |  |  | Senior Solutions Engineer | Adobe | Engineer | 29–32
Scaled Rollout and Adoption | Advanced Training - Partners + Contribution | Deliver deep-dive workshops |  |  | Senior Solutions Engineer | Adobe | Engineer | 29–32
Scaled Rollout and Adoption | Advanced Training - Partners + Contribution | Assess capability maturity |  |  | Senior Solutions Engineer | Adobe | Engineer | 29–32
Scaled Rollout and Adoption | Advanced Training - Partners + Contribution | Recognize high-performing contributors | Advanced Enablement Program | Deep-dive enablement for partner contributions. | Senior Solutions Engineer | Adobe | Engineer | 29–32
Scaled Rollout and Adoption | Phase Gate Strategic Recommendations + Documentation | Review milestone progress |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–32
Scaled Rollout and Adoption | Phase Gate Strategic Recommendations + Documentation | Conduct readiness evaluation |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–32
Scaled Rollout and Adoption | Phase Gate Strategic Recommendations + Documentation | Document lessons learned |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–32
Scaled Rollout and Adoption | Phase Gate Strategic Recommendations + Documentation | Prepare scale-up recommendations | Scaled Rollout Readiness Review | Formal phase gate review and recommendations. | Senior Solutions Engineer | Knapsack | Engineer | 21–32
Scaled Rollout and Adoption | Pre-Cutover Readiness Review | Verify technical and operational prerequisites |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Pre-Cutover Readiness Review | Conduct dry-run deployment |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Pre-Cutover Readiness Review | Validate SSO and environment stability |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Pre-Cutover Readiness Review | Approve readiness sign-off | Cutover Readiness Checklist, Technical Validation Sign-off, Risk Mitigation Plan | Validate all technical, operational, and training prerequisites; confirm SSO, component rendering, deployment readiness before final rollout. | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Data & Configuration Freeze | Lock repositories and configuration files |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Data & Configuration Freeze | Capture environment snapshot |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Data & Configuration Freeze | Validate rollback plan |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Data & Configuration Freeze | Communicate freeze timeline | Configuration Freeze Log, Environment Snapshot | Lock configuration and repositories; capture environment snapshot for rollback if needed before go-live. | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Final UAT & Stakeholder Acceptance | Develop UAT scripts |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Final UAT & Stakeholder Acceptance | Facilitate sessions with pilot users |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Final UAT & Stakeholder Acceptance | Log and triage issues |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Final UAT & Stakeholder Acceptance | Capture sign-off from business owners | UAT Sign-off Report, Known Issues Log | Conduct final user acceptance testing with pilot teams; log and triage known issues before launch. | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Change Impact Analysis | Identify impacted teams |  |  | CX Partner - Change Management SME | Knapsack | CX Partner | 21–24
Scaled Rollout and Adoption | Change Impact Analysis | Conduct stakeholder interviews |  |  | CX Partner - Change Management SME | Knapsack | CX Partner | 21–24
Scaled Rollout and Adoption | Change Impact Analysis | Document change action plans |  |  | CX Partner - Change Management SME | Knapsack | CX Partner | 21–24
Scaled Rollout and Adoption | Change Impact Analysis | Share mitigation strategies | Change Impact Log, Stakeholder Action Plan | Evaluate and manage business unit impacts during scale-up. | CX Partner - Change Management SME | Knapsack | CX Partner | 21–24
Scaled Rollout and Adoption | Adoption Acceleration Campaign | Develop success-story series |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 29–32
Scaled Rollout and Adoption | Adoption Acceleration Campaign | Publish awareness materials |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 29–32
Scaled Rollout and Adoption | Adoption Acceleration Campaign | Monitor engagement analytics |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 29–32
Scaled Rollout and Adoption | Adoption Acceleration Campaign | Share outcomes in adoption dashboard | Awareness Campaign, Success Story Series | Promote awareness and highlight early success stories to drive adoption. | CX Partner - Change Management SME | Adobe | CX Partner | 29–32
Scaled Rollout and Adoption | Partner Enablement & Recognition | Define contribution metrics |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 29–32
Scaled Rollout and Adoption | Partner Enablement & Recognition | Build leaderboard dashboard |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 29–32
Scaled Rollout and Adoption | Partner Enablement & Recognition | Communicate recognition framework |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 29–32
Scaled Rollout and Adoption | Partner Enablement & Recognition | Host partner recognition event | Partner Contribution Leaderboard, Recognition Plan | Drive engagement through recognition and contribution metrics. | CX Partner - Change Management SME | Adobe | CX Partner | 29–32
Optimization and Continued Support | Transition support | Conduct lessons-learned session |  |  | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Transition support | Update improvement backlog |  |  | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Transition support | Create continuous improvement plan |  |  | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Transition support | Share analytics summary | Continuous Improvement Plan | Continuous improvement plan with analytics and recommendations. | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Cutover Execution | Perform production deployment |  |  | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Cutover Execution | Validate access and permissions |  |  | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Cutover Execution | Monitor service health dashboard |  |  | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Cutover Execution | Confirm deployment sign-off | Deployment Completion Report, Access Validation, Service Health Dashboard | Execute production deployment; validate access controls, deployment integrity, and service health. | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Go-Live Communication Launch | Draft go-live announcement and FAQ |  |  | Project Manager | Adobe | Project Manager | 33+
Optimization and Continued Support | Go-Live Communication Launch | Coordinate internal distribution |  |  | Project Manager | Adobe | Project Manager | 33+
Optimization and Continued Support | Go-Live Communication Launch | Activate support channels |  |  | Project Manager | Adobe | Project Manager | 33+
Optimization and Continued Support | Go-Live Communication Launch | Collect user questions for knowledge base | Internal Announcement, Go-Live FAQ, Support Channels | Announce official go-live to stakeholders; provide communication templates and support channels. | Project Manager | Adobe | Project Manager | 33+
Optimization and Continued Support | Hypercare Phase (Post-Go-Live Support) | Provide high-touch post-launch support |  |  | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Hypercare Phase (Post-Go-Live Support) | Monitor tickets and SLAs |  |  | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Hypercare Phase (Post-Go-Live Support) | Resolve critical issues |  |  | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Hypercare Phase (Post-Go-Live Support) | Deliver weekly hypercare reports | Hypercare Status Reports, Issue Resolution Tracker | Provide high-touch support for 30–90 days post go-live, track SLAs, and stabilize the system. | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Post-Implementation Review | Analyze KPIs and satisfaction metrics |  |  | Project Manager | Adobe | Project Manager | 33+
Optimization and Continued Support | Post-Implementation Review | Conduct stakeholder debrief |  |  | Project Manager | Adobe | Project Manager | 33+
Optimization and Continued Support | Post-Implementation Review | Document lessons learned |  |  | Project Manager | Adobe | Project Manager | 33+
Optimization and Continued Support | Post-Implementation Review | Prepare optimization backlog | Lessons Learned Summary, KPI Report, Optimization Backlog | Evaluate performance, adoption, and partner satisfaction to inform optimization roadmap. | Project Manager | Adobe | Project Manager | 33+
Optimization and Continued Support | Transition to Steady-State Operations | Facilitate knowledge transfer sessions |  |  | Design System Lead | Adobe | Design Lead | 33+
Optimization and Continued Support | Transition to Steady-State Operations | Deliver ownership matrix |  |  | Design System Lead | Adobe | Design Lead | 33+
Optimization and Continued Support | Transition to Steady-State Operations | Confirm governance cadence |  |  | Design System Lead | Adobe | Design Lead | 33+
Optimization and Continued Support | Transition to Steady-State Operations | Transition documentation to internal owners | Knowledge Transfer Documentation, Ownership Matrix, Future Roadmap | Transition ownership to internal design ops and engineering teams; confirm governance cadence. | Design System Lead | Adobe | Design Lead | 33+
Optimization and Continued Support | Continuous Improvement Framework | Develop sentiment tracking dashboards |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 33+
Optimization and Continued Support | Continuous Improvement Framework | Monitor adoption trends |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 33+
Optimization and Continued Support | Continuous Improvement Framework | Recommend process improvements |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 33+
Optimization and Continued Support | Continuous Improvement Framework | Report quarterly metrics | Adoption Dashboards, Sentiment Trend Reports | Maintain engagement and track long-term adoption trends. | CX Partner - Change Management SME | Adobe | CX Partner | 33+
Optimization and Continued Support | Strategic Partnership Review | Conduct quarterly business reviews |  |  | CX Partner - Change Management SME | Knapsack | CX Partner | 33+
Optimization and Continued Support | Strategic Partnership Review | Analyze partnership performance |  |  | CX Partner - Change Management SME | Knapsack | CX Partner | 33+
Optimization and Continued Support | Strategic Partnership Review | Identify collaboration opportunities |  |  | CX Partner - Change Management SME | Knapsack | CX Partner | 33+
Optimization and Continued Support | Strategic Partnership Review | Update partnership roadmap | Quarterly Business Review Deck | Evaluate ongoing partnership alignment and strategic direction. | CX Partner - Change Management SME | Knapsack | CX Partner | 33+
Optimization and Continued Support | Case Study Development | Collect success metrics and outcomes |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 33+
Optimization and Continued Support | Case Study Development | Draft internal case study |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 33+
Optimization and Continued Support | Case Study Development | Obtain approvals for publishing |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 33+
Optimization and Continued Support | Case Study Development | Archive case study in program library | Internal Case Study + Success Metrics | Document program success and outcomes for future scaling. | CX Partner - Change Management SME | Adobe | CX Partner | 33+
Implementation + Onboarding | Design System Charter & Reference Architecture | Define design system scope, tiering (core vs product), and success metrics (JTBD + KPIs) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 2–3
Implementation + Onboarding | Design System Charter & Reference Architecture | Align stakeholders on governance model (decision rights, contribution, release ownership) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 2–3
Implementation + Onboarding | Design System Charter & Reference Architecture | Draft reference architecture (tokens → packages → docs → integrations) and data flows |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 2–3
Implementation + Onboarding | Design System Charter & Reference Architecture | Define adoption measurement plan (usage, drift, quality, velocity) and instrumentation points |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 2–3
Implementation + Onboarding | Design System Charter & Reference Architecture | Finalize charter and publish operating cadence | Design System Charter + Reference Architecture | Charter, KPIs, governance, and reference architecture diagram for the design↔code system. | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 2–3
Implementation + Onboarding | Foundations & Token Taxonomy | Audit existing foundations (color/type/spacing/elevation/motion/icons) and define target standards |  |  | Knapsack - Design System Lead | Knapsack | Design Lead | 3–4
Implementation + Onboarding | Foundations & Token Taxonomy | Define token taxonomy (global/semantic/component) and naming conventions |  |  | Knapsack - Design System Lead | Knapsack | Design Lead | 3–4
Implementation + Onboarding | Foundations & Token Taxonomy | Define theming model (brand themes, dark mode, high contrast) and constraints |  |  | Knapsack - Design System Lead | Knapsack | Design Lead | 3–4
Implementation + Onboarding | Foundations & Token Taxonomy | Define content and accessibility guidelines for foundations (contrast, typography, motion) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 3–4
Implementation + Onboarding | Foundations & Token Taxonomy | Create token governance rules (who can change what, versioning, approvals) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 3–4
Implementation + Onboarding | Foundations & Token Taxonomy | Publish foundations + token spec in design + docs | Foundations + Token Specification | Foundations standards and token taxonomy/naming/theming/governance guidance. | Knapsack - Design System Lead | Knapsack | Design Lead | 3–4
Implementation + Onboarding | Token Pipeline Build & Theming Strategy | Select/confirm token tooling and define source of truth (design vs repo) rules |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Implementation + Onboarding | Token Pipeline Build & Theming Strategy | Implement token export/build pipeline (validation, transforms, outputs) |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–6
Implementation + Onboarding | Token Pipeline Build & Theming Strategy | Generate platform outputs (web JSON/CSS vars; add others if needed) and verify integrity |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–6
Implementation + Onboarding | Token Pipeline Build & Theming Strategy | Implement theme packaging and switching strategy (e.g., multiple brands / modes) |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–6
Implementation + Onboarding | Token Pipeline Build & Theming Strategy | Set up CI checks for token schema validation and breaking-change detection |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–6
Implementation + Onboarding | Token Pipeline Build & Theming Strategy | Document token contribution + release workflow | Token Pipeline + Theme Artifacts | Automated token build outputs, theming strategy, CI validation, and contribution workflow. | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Implementation + Onboarding | Component Inventory & Prioritization | Inventory existing components and map to user journeys / product surfaces |  |  | Knapsack - Design System Lead | Knapsack | Design Lead | 2–3
Implementation + Onboarding | Component Inventory & Prioritization | Define component maturity levels and acceptance criteria (spec completeness, a11y, tests) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 2–3
Implementation + Onboarding | Component Inventory & Prioritization | Prioritize MVP component set and create backlog with sequencing |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 2–3
Implementation + Onboarding | Component Inventory & Prioritization | Define component spec template (anatomy, states, content rules, accessibility, tokens) |  |  | Knapsack - Design System Lead | Knapsack | Design Lead | 2–3
Implementation + Onboarding | Component Inventory & Prioritization | Publish component roadmap and MVP scope | Component Inventory + MVP Roadmap | Inventory, prioritization matrix, MVP scope, and backlog sequencing. | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 2–3
Implementation + Onboarding | Component API Standards & Templates | Define component API patterns (props, composition, slots, variants) and naming conventions |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–4
Implementation + Onboarding | Component API Standards & Templates | Define accessibility patterns per component type (keyboard, focus, ARIA, semantics) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 3–4
Implementation + Onboarding | Component API Standards & Templates | Create starter templates for component implementation and tests |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–4
Implementation + Onboarding | Component API Standards & Templates | Define contribution workflow (RFC, review gates, required artifacts) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 3–4
Implementation + Onboarding | Component API Standards & Templates | Publish standards in docs and align with code owners | Component Standards + Contribution Model | Component API standards, a11y patterns, templates, and contribution/review workflow. | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–4
Implementation + Onboarding | Code Connect Strategy & Configuration | Define Code Connect coverage targets and connected-component definition (source of truth) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 2–4
Implementation + Onboarding | Code Connect Strategy & Configuration | Set up Code Connect configuration and repo/package references |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 2–4
Implementation + Onboarding | Code Connect Strategy & Configuration | Define mapping conventions (component IDs, variants/states, props) and ownership model |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 2–4
Implementation + Onboarding | Code Connect Strategy & Configuration | Implement initial mappings for MVP components and verify accuracy |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 2–4
Implementation + Onboarding | Code Connect Strategy & Configuration | Define drift detection + remediation workflow (design↔code mismatch) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 2–4
Implementation + Onboarding | Code Connect Strategy & Configuration | Publish Code Connect playbook and governance | Code Connect Setup + Drift Governance | Connected component strategy, configuration, mapping conventions, and drift SOP. | Knapsack - Design System / Platform SME | Knapsack | SME | 2–4
Implementation + Onboarding | Documentation IA & Templates (Design System Docs) | Define docs information architecture (Foundations, Tokens, Components, Patterns, Content, A11y) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 2–3
Implementation + Onboarding | Documentation IA & Templates (Design System Docs) | Create docs templates (component pages, token pages, pattern pages, migration guides) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 2–3
Implementation + Onboarding | Documentation IA & Templates (Design System Docs) | Set up docs site scaffold and navigation (or align existing docs site) |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 2–3
Implementation + Onboarding | Documentation IA & Templates (Design System Docs) | Create “Getting Started” guides for designers, engineers, and partners |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 2–3
Implementation + Onboarding | Documentation IA & Templates (Design System Docs) | Publish initial docs structure and ownership/freshness rules | Design System Documentation IA + Templates | Docs structure, page templates, and ownership/freshness model for living documentation. | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 2–3
Implementation + Onboarding | Quality Gates Setup (A11y, Visual, Performance, Security) | Define quality gate policy (release criteria for components/tokens/docs) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 3–5
Implementation + Onboarding | Quality Gates Setup (A11y, Visual, Performance, Security) | Set up accessibility automation (linting, test utilities, checks) and manual audit process |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–5
Implementation + Onboarding | Quality Gates Setup (A11y, Visual, Performance, Security) | Set up visual regression testing and baseline snapshot workflow |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–5
Implementation + Onboarding | Quality Gates Setup (A11y, Visual, Performance, Security) | Define performance budgets for components and measurement approach |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–5
Implementation + Onboarding | Quality Gates Setup (A11y, Visual, Performance, Security) | Review secure publishing pipeline (dependency policy, provenance/signing if applicable) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 3–5
Implementation + Onboarding | Quality Gates Setup (A11y, Visual, Performance, Security) | Publish QA checklist and integrate gates into CI/CD | Quality Gates + Automation Framework | Automated quality checks (a11y/visual/perf/security) and release gating policy. | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–5
Implementation + Onboarding | Release Engineering & Package Strategy | Define repo strategy (mono/polyrepo) and package boundaries |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–5
Implementation + Onboarding | Release Engineering & Package Strategy | Define semantic versioning, changelog, and release notes standards |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 3–5
Implementation + Onboarding | Release Engineering & Package Strategy | Implement CI/CD for build/test/publish packages and deploy docs |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–5
Implementation + Onboarding | Release Engineering & Package Strategy | Set up compatibility testing (breaking changes, supported versions matrix) |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–5
Implementation + Onboarding | Release Engineering & Package Strategy | Define deprecation and migration policy (sunset timelines, migration guides) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 3–5
Implementation + Onboarding | Release Engineering & Package Strategy | Publish release playbook and ownership | Release Playbook + CI/CD Pipelines | Package strategy, semver/release standards, CI/CD pipelines, and compatibility policy. | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 3–5
Implementation + Onboarding | AI Contextual Capabilities – Context Model & Knowledge Base | Define AI JTBD and supported user journeys (recommend, explain, generate safely, lint) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Implementation + Onboarding | AI Contextual Capabilities – Context Model & Knowledge Base | Define context schema/ontology (product, platform, theme, constraints, persona) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Implementation + Onboarding | AI Contextual Capabilities – Context Model & Knowledge Base | Curate knowledge sources (docs, tokens, component specs, governance rules) and ownership |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Implementation + Onboarding | AI Contextual Capabilities – Context Model & Knowledge Base | Implement retrieval/indexing approach (metadata/tags + search/index; freshness rules) |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–6
Implementation + Onboarding | AI Contextual Capabilities – Context Model & Knowledge Base | Define prompt patterns and response formats tied to system entities (tokens/components/patterns) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Implementation + Onboarding | AI Contextual Capabilities – Context Model & Knowledge Base | Establish human-in-the-loop review and escalation paths for risky outputs |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 4–6
Implementation + Onboarding | AI Contextual Capabilities – Context Model & Knowledge Base | Publish AI context design and operations plan | AI Context Model + Knowledge Base Plan | Context schema, curated sources, retrieval approach, prompt patterns, and governance plan. | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Scaled Rollout and Adoption | Component Library MVP Build (Core Set) | Implement MVP component set in code (per roadmap) with tokens wired-in |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 6–10
Scaled Rollout and Adoption | Component Library MVP Build (Core Set) | Create component tests (unit/integration) and a11y coverage per standards |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 6–10
Scaled Rollout and Adoption | Component Library MVP Build (Core Set) | Build usage examples and recipes for each MVP component |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 6–10
Scaled Rollout and Adoption | Component Library MVP Build (Core Set) | Run design↔code alignment review (spec conformance, states, variants) |  |  | Knapsack - Design System Lead | Knapsack | Design Lead | 6–10
Scaled Rollout and Adoption | Component Library MVP Build (Core Set) | Publish packages and docs for MVP components |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 6–10
Scaled Rollout and Adoption | Component Library MVP Build (Core Set) | Pilot adoption with 1–2 product teams and collect issues |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 6–10
Scaled Rollout and Adoption | Component Library MVP Build (Core Set) | Refine based on pilot feedback and finalize MVP release | MVP Component Library Release | Published component packages + docs + examples for the MVP set, validated by pilot teams. | Knapsack - Design Systems Engineer | Knapsack | Engineer | 6–10
Scaled Rollout and Adoption | Code Connect Coverage Expansion & Drift Remediation | Expand Code Connect mappings to additional high-value components |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–6
Scaled Rollout and Adoption | Code Connect Coverage Expansion & Drift Remediation | Validate mappings across variants/states and align naming/props |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–6
Scaled Rollout and Adoption | Code Connect Coverage Expansion & Drift Remediation | Establish drift reporting (coverage, freshness, mismatch categories) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Scaled Rollout and Adoption | Code Connect Coverage Expansion & Drift Remediation | Run drift remediation cycles with code/design owners |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 4–6
Scaled Rollout and Adoption | Code Connect Coverage Expansion & Drift Remediation | Document common drift patterns and prevention guidance |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Scaled Rollout and Adoption | Code Connect Coverage Expansion & Drift Remediation | Publish connected coverage dashboard and SOP | Code Connect Coverage + Drift Dashboard | Expanded connected coverage with drift reporting, remediation workflow, and dashboards. | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–6
Scaled Rollout and Adoption | Docs Launch + Recipes & Migration Guides | Publish foundations, tokens, and component standards in docs site |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 3–5
Scaled Rollout and Adoption | Docs Launch + Recipes & Migration Guides | Publish recipes/patterns library (common flows, layouts, accessibility patterns) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 3–5
Scaled Rollout and Adoption | Docs Launch + Recipes & Migration Guides | Create migration guides for adopting new packages/components (including deprecations) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 3–5
Scaled Rollout and Adoption | Docs Launch + Recipes & Migration Guides | Add embedded code samples and playground links (governed snippet sources) |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–5
Scaled Rollout and Adoption | Docs Launch + Recipes & Migration Guides | Launch docs and establish update cadence + ownership model | Design System Docs v1 Launch | Published docs with recipes, migration guides, governed snippets, and ownership cadence. | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 3–5
Scaled Rollout and Adoption | Partner Contribution Pathway & Certification | Define partner contribution workflow (intake, sandbox, review gates, SLAs) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 3–5
Scaled Rollout and Adoption | Partner Contribution Pathway & Certification | Create partner contribution kit (templates, checklists, example PRs) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 3–5
Scaled Rollout and Adoption | Partner Contribution Pathway & Certification | Define certification rubric (design + code + a11y + tests + documentation) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 3–5
Scaled Rollout and Adoption | Partner Contribution Pathway & Certification | Implement badges/labels for certified components/patterns in docs |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–5
Scaled Rollout and Adoption | Partner Contribution Pathway & Certification | Pilot partner contribution with 1 partner and iterate workflow |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 3–5
Scaled Rollout and Adoption | Partner Contribution Pathway & Certification | Launch partner pathway program and publish certification criteria | Partner Contribution + Certification Program | Partner workflow, certification rubric, and publishing mechanics for approved contributions. | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 3–5
Scaled Rollout and Adoption | AI Contextual Capabilities – Workflow Integrations | Design AI assistant experiences for designers (Figma) and engineers (docs/IDE) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 4–8
Scaled Rollout and Adoption | AI Contextual Capabilities – Workflow Integrations | Implement Figma-side entry point (plugin/UI) for contextual recommendations and linting |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–8
Scaled Rollout and Adoption | AI Contextual Capabilities – Workflow Integrations | Implement docs-site assistant for contextual guidance and search/Q&A |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–8
Scaled Rollout and Adoption | AI Contextual Capabilities – Workflow Integrations | Implement IDE/PR assistant hooks (optional) for component/token guidance and compliance |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–8
Scaled Rollout and Adoption | AI Contextual Capabilities – Workflow Integrations | Add human approval flow for risky actions (generation, large refactors) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 4–8
Scaled Rollout and Adoption | AI Contextual Capabilities – Workflow Integrations | Pilot integrations with selected teams and capture feedback | AI Workflow Integrations MVP | Initial AI integration points (Figma/docs/IDE as applicable) piloted with teams. | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 4–8
Scaled Rollout and Adoption | AI Contextual Capabilities – Evaluation Harness + Telemetry | Define evaluation metrics (accuracy, policy compliance, latency, satisfaction) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Scaled Rollout and Adoption | AI Contextual Capabilities – Evaluation Harness + Telemetry | Create golden test set (prompts + expected outcomes) based on real workflows |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Scaled Rollout and Adoption | AI Contextual Capabilities – Evaluation Harness + Telemetry | Implement automated evaluation harness and regression checks |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–6
Scaled Rollout and Adoption | AI Contextual Capabilities – Evaluation Harness + Telemetry | Instrument telemetry (queries, acceptance, edits, failures, drift incidents) |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–6
Scaled Rollout and Adoption | AI Contextual Capabilities – Evaluation Harness + Telemetry | Set up dashboards and feedback triage workflow |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 4–6
Scaled Rollout and Adoption | AI Contextual Capabilities – Evaluation Harness + Telemetry | Run first eval cycle and iterate prompts/retrieval based on results | AI Evaluation + Telemetry Dashboard | Automated eval suite and telemetry dashboards with a triage/iteration workflow. | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Optimization and Continued Support | Continuous Quality & Accessibility Automation | Maintain and expand a11y and visual regression baselines as components grow |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | Ongoing
Optimization and Continued Support | Continuous Quality & Accessibility Automation | Perform periodic audits (a11y, performance) and track remediation backlog |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | Ongoing
Optimization and Continued Support | Continuous Quality & Accessibility Automation | Add new quality gates based on incident learnings and drift patterns |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | Ongoing
Optimization and Continued Support | Continuous Quality & Accessibility Automation | Publish quarterly quality report (issues, fixes, risk areas) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | Ongoing
Optimization and Continued Support | Continuous Quality & Accessibility Automation | Refine QA playbooks and contributor checklists | Quarterly Quality + A11y Report | Ongoing quality automation upkeep with periodic reporting and remediation tracking. | Knapsack - Design System / Platform SME | Knapsack | SME | Ongoing
Optimization and Continued Support | Release Cadence, Deprecations & Migrations | Run regular release cadence (monthly/quarterly) with changelog automation |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | Ongoing
Optimization and Continued Support | Release Cadence, Deprecations & Migrations | Execute deprecations per policy and maintain migration guides |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | Ongoing
Optimization and Continued Support | Release Cadence, Deprecations & Migrations | Support teams through upgrades (office hours, PR assistance, issue triage) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | Ongoing
Optimization and Continued Support | Release Cadence, Deprecations & Migrations | Monitor compatibility and fix regressions quickly |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | Ongoing
Optimization and Continued Support | Release Cadence, Deprecations & Migrations | Publish release communications and adoption notes | Release Cadence + Migration Program | Defined cadence with deprecation/migration support and consistent release communications. | Knapsack - Program/Delivery PM | Knapsack | Project Manager | Ongoing
Optimization and Continued Support | Adoption Analytics & Reporting (Design↔Code) | Instrument usage analytics (package installs, component usage, token usage) where possible |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | Ongoing
Optimization and Continued Support | Adoption Analytics & Reporting (Design↔Code) | Define adoption KPIs and reporting views per persona (design, eng, leadership) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | Ongoing
Optimization and Continued Support | Adoption Analytics & Reporting (Design↔Code) | Publish monthly adoption report and insights (hotspots, gaps, drift) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | Ongoing
Optimization and Continued Support | Adoption Analytics & Reporting (Design↔Code) | Maintain backlog of adoption friction and prioritize fixes | Adoption Analytics Dashboard + Monthly Report | Ongoing analytics and reporting across design↔code adoption and system health. | Knapsack - Program/Delivery PM | Knapsack | Project Manager | Ongoing
Optimization and Continued Support | AI Contextual Capabilities – Guardrails, Governance & Iteration | Implement/maintain guardrails (allowed actions, policy filters, safe defaults) |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | Ongoing
Optimization and Continued Support | AI Contextual Capabilities – Guardrails, Governance & Iteration | Define AI governance board/cadence (changes, incident response, approvals) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | Ongoing
Optimization and Continued Support | AI Contextual Capabilities – Guardrails, Governance & Iteration | Run regular eval + telemetry reviews and prioritize improvements |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | Ongoing
Optimization and Continued Support | AI Contextual Capabilities – Guardrails, Governance & Iteration | Improve retrieval quality (metadata, freshness, coverage) and reduce hallucinations |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | Ongoing
Optimization and Continued Support | AI Contextual Capabilities – Guardrails, Governance & Iteration | Document AI change log and communicate capability updates |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | Ongoing
Optimization and Continued Support | AI Contextual Capabilities – Guardrails, Governance & Iteration | Conduct periodic privacy/security review for AI integrations and data handling | AI Governance + Guardrails Program | Ongoing guardrails, governance cadence, eval/telemetry reviews, and privacy/security checks. | Knapsack - Design System / Platform SME | Knapsack | SME | Ongoing
Optimization and Continued Support | AI Contextual Capabilities – Feedback Loop + Knowledge Refresh | Triage user feedback and tag gaps (missing docs, components, patterns) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | Ongoing
Optimization and Continued Support | AI Contextual Capabilities – Feedback Loop + Knowledge Refresh | Refresh knowledge base and prompts when system changes (tokens/components/releases) |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | Ongoing
Optimization and Continued Support | AI Contextual Capabilities – Feedback Loop + Knowledge Refresh | Measure impact of improvements (acceptance rate, reduced support tickets) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | Ongoing
Optimization and Continued Support | AI Contextual Capabilities – Feedback Loop + Knowledge Refresh | Publish quarterly AI capability maturity update | Quarterly AI Context Refresh + Impact Report | Feedback-driven updates to knowledge/prompting with measured impact reporting. | Knapsack - Program/Delivery PM | Knapsack | Project Manager | Ongoing

## Summary
Estimation Summary
Delivery Model |  |  | Total Hours
Journey |  |  | Total Cost
Deployment
Default Complexity
Readiness Level
Readiness Multiplier
Hours & Cost by Phase
Phase | Hours | Cost
Implementation + Onboarding
Scaled Rollout and Adoption
Optimization and Continued Support
Hours & Cost by Provider
Provider | Hours | Cost
Knapsack
Client/SCE
Hours & Cost by Standard Role
Standard Role | Hours | Cost
CX Partner
Project Manager
Solution Analyst
Senior Solution Analyst
SME
Executive

## RAID Log
ID | Type | Title | Description | Owner | Impact (1-5) | Probability (1-5) | Score | Status | Mitigation / Next Steps | Due Date | Date Opened | Date Closed | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200

## Instructions - Adobe
Adobe Resource Planning Model v2.0 — How to:
1) Review the Plan Tab
- Milestone Plan Tab drives the Proposed Solutions tab: Rollups by Role for review
2) Adjust the Accountable Party Column F
- Amber took a first pass at the scrub - Angelie and team take it away!
3 ) Review the Summary Tab to understand the impact on the Resource Model
- The RACI align with where we land on scope in the Procurement phase we are currently in

## Milestone Plan
Line # | Milestone (Activity) | Phase (auto) | Deliverable (auto) | Description | Knapsack Role Description | Accountable Party | Role | Effort Type | Effort Value | Complexity | Calc Hours | Weeks (FTE) | Start Date | End Date | Hourly Rate | Daily Rate | Cost (auto) | Notes | Scenario Hour Mult. | Scenario Rate Mult. | Contingency % | Final Hours (auto) | Adj. Hourly Rate | Adj. Cost (auto) | Review Notes
1 | Program management and Steering Committee coordination |  |  | Kickoff, bi-weekly stand-ups, monthly reports, phase gate reviews |  | Adobe |  | FTE | 0.01 | Low | 100 | [13 empty] | potentially
2 | Facilitating and supporting deliverables |  |  | Track adoption metrics, stakeholder engagement, and training completion |  | Adobe | Adobe | FTE | 0.03 | Medium | [14 empty] | typically owned by the team - partnership with Program management + leads
3 | Stakeholder Alignment Workshops |  |  | Ensure executive and stakeholder alignment before kickoff. |  | Adobe | Adobe | FTE | 0.03 | Medium | [14 empty] | Product Owners, etc.
4 | Change Readiness Assessment |  |  | Assess cultural, technical, and operational readiness prior to implementation. |  | Adobe | CX Partner - Change Management SME | FTE | 0.03 | Medium | 16 | [13 empty] | The Spectrum team will be fine - external to Spectrum will be limited to the documentation. Programming is in place to support this | Amber to share the readiness survey
5 | Program management and coordination |  |  | Program coordination, kickoff, and phase review oversight |  | Knapsack |  | FTE | 0.03 | Medium | [14 empty] | @ADOBE - WE HAVE INCLUDED OUR PROJECT MANAGER RESOURCE HERE TO SUPPORT AND THEY WILL TAKE DIRECTION FROM ANDREW AND I AS CX PARTNERS TO KEEP COST DOWN AND STILL PROVIDE YOU WITH THE VALUE OF CX LED PROGRAM MANAGEMENT. THEY WILL NEED TO BE IN LOCK STEP WITH YOUR PROJECT MANAGER FROM ROW 1 OF THIS PLAN. 10.28 @ADOBE - what is the final answer on this? Is Adobe Accountable OR do you want/need Knapsack support. Notes from previous review. Our Program Managers are stretched quite thin - IF there is an opportunity to leverage a Project Manager alongside the FDE we can consider it - let's align on the terms. Option for contractor spend
6 | Communication Launch Plan |  |  | Launch program messaging, goals, and brand identity across teams. |  | Adobe | Adobe | FTE | 0.05 | High
7 | Preparation |  |  | Verify infrastructure readiness, environment setup, and permissions |  | Knapsack |  | FTE | 0.025 | Medium
8 | Local install support |  |  | Validate local environment setup for Knapsack and IPE components |  | Knapsack |  | FTE | 0.03 | Medium
9 | Component rendering |  |  | Validate successful rendering of Spectrum components across environments |  | Knapsack |  | FTE | 0.05 | High
10 | SME support for rendering |  |  | SME oversight of rendering logic and architectural consistency |  | Knapsack |  | FTE | 0.025 | Medium
11 | Deployment support |  |  | Plan and validate deployment pipelines with measurable success criteria |  | Knapsack |  | FTE | 0.025 | Medium
12 | FDE led Implementation + Architecture + Governance |  |  | Define architecture, component contribution model, accessibility, governance framework |  | Knapsack |  | FTE | 0.03 | Medium | [7 empty] | This is your Forward Deployed Engineer who will be accountable for phased Milestone Activities.
13 | Stakeholder Interviews/Workshops |  |  | Collect stakeholder inputs and align roadmap |  | Knapsack |  | FTE | 0.025 | Medium
14 | Pilot Enablement & Feedback Loop |  |  | Gather early adopter feedback and adjust onboarding approach. |  | Adobe | Adobe | FTE | 0.05 | High
15 | Role-Based Training Enablement |  |  | Deliver tailored enablement by persona to improve comprehension and adoption. |  | Adobe | Adobe | FTE | 0.05 | High
16 | SME support for Deployment/DevOps |  |  | Validate CI/CD, cloud authoring, and deployment automation readiness |  | Knapsack |  | FTE | 0.03 | Medium | [14 empty] | Reference the playbook to support understanding here
17 | Cloud authoring setup and testing |  |  | Setup and validate authoring in cloud environments |  | Knapsack |  | FTE | 0.05 | High
18 | SSO setup and testing |  |  | Configure and test single sign-on with enterprise identity provider |  | Knapsack |  | FTE | 0.03 | Medium | [7 empty] | This is a medium effort IF Adobe speaks vanilla SAML SSO | [6 empty] | Reference the playbook to support understanding here
19 | Training - Eng / UX / Partners |  |  | Integrated training for engineering, UX, and partner audiences |  | Adobe |  | FTE | 0.05 | High | [14 empty] | Adobe practice today
20 | Workflow Diagrams |  |  | Map self-service contribution and implementation workflows |  | Knapsack |  | FTE | 0.025 | Medium | [14 empty] | Adobe practice today - might be a better choice for Knapsack to own. Adobe Responsible for the intitial recommended workflows. To be tested and validated in support of the curriculum
21 | Content planning and integration |  |  | Documentation for web, React, iOS, Android implementations | Adobe | Knapsack |  | FTE | 0.05 | High | [14 empty] | Adobe practice today - the content planning aspect is owned by Adobe - the documentation of the guides is driven by Knapsack. Shared Responsibility. Adobe is Accountable for authoring the the guides + FDE is Responsible for review. To be reflected in the RACI
22 | Advanced Training - Partners + Contribution |  |  | Deep-dive enablement for partner contributions |  | Adobe |  | FTE | 0.03 | Medium | [14 empty] | Knapsack to provide the fodder
23 | Phase Gate Strategic Recommendations + Documentation |  |  | Formal phase gate review and recommendations |  | Knapsack |  | FTE | 0.025 | Medium
24 | Pre-Cutover Readiness Review |  |  | Validate all technical, operational, and training prerequisites; confirm SSO, component rendering, deployment readiness before final rollout. |  | Knapsack |  | FTE | 0.025 | Medium
25 | Data & Configuration Freeze |  |  | Lock configuration and repositories; capture environment snapshot for rollback if needed before go-live. |  | Knapsack |  | FTE | 0.025 | Medium
26 | Final UAT & Stakeholder Acceptance |  |  | Conduct final user acceptance testing with pilot teams; log and triage known issues before launch. |  | Knapsack |  | FTE | 0.025 | Medium | [14 empty] | Shared Responsibility. Adobe is Accountable for authoring the test scripts, identifying the UAT participants, and ensuring that timelines are kept, and Knapsack FDE is Responsible to ensure that bug/fixes are prioritized and addresssed.
27 | Change Impact Analysis |  |  | Evaluate and manage business unit impacts during scale-up. |  | Knapsack |  | FTE | 0.05 | High | [14 empty] | Knapsack CX Partner will sit on the Steering Committee to provide coaching for all Activities that Adobe is ACCOUNTABLE for (Column G) where KS Roles are typically in delivery (Column H) to be reflected in the Steering Committe/Governance Model + RACI
28 | Adoption Acceleration Campaign |  |  | Promote awareness and highlight early success stories to drive adoption. |  | Adobe | Adobe | FTE | 0.05 | High
29 | Partner Enablement & Recognition |  |  | Drive engagement through recognition and contribution metrics. |  | Adobe | Adobe | FTE | 0.05 | High
30 | Transition support |  |  | Continuous improvement plan with analytics and recommendations |  | Knapsack |  | FTE | 0.025 | Low
31 | Cutover Execution |  |  | Execute production deployment; validate access controls, deployment integrity, and service health. |  | Knapsack |  | FTE | 0.05 | Low
32 | Go-Live Communication Launch |  |  | Announce official go-live to stakeholders; provide communication templates and support channels. |  | Adobe |  | FTE | 0.03 | Medium
33 | Hypercare Phase (Post-Go-Live Support) |  |  | Provide high-touch support for 30–90 days post go-live, track SLAs, and stabilize the system. |  | Knapsack |  | FTE | 0.03 | Medium
34 | Post-Implementation Review |  |  | Evaluate performance, adoption, and partner satisfaction to inform optimization roadmap. |  | Adobe |  | FTE | 0.03 | Medium
35 | Transition to Steady-State Operations |  |  | Transition ownership to internal design ops and engineering teams; confirm governance cadence. |  | Adobe |  | FTE | 0.05 | High
36 | Continuous Improvement Framework |  |  | Maintain engagement and track long-term adoption trends. |  | Adobe | Adobe | FTE | 0.03 | Medium
37 | Strategic Partnership Review |  |  | Evaluate ongoing partnership alignment and strategic direction. |  | Knapsack | Adobe | FTE | 0.03 | Medium
38 | Case Study Development |  |  | Document program success and outcomes for future scaling. |  | Adobe |  | FTE | 0.03 | Medium
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400

## WBS
Phase | Activity / Milestone | Subtask | Deliverable | Deliverable Description | Knapsack Role Description | Accountable Party | Role | Timeline (Weeks)
Implementation + Onboarding | Stakeholder Alignment Workshops | Identify executive and operational stakeholders |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 1–2
Implementation + Onboarding | Stakeholder Alignment Workshops | Conduct alignment workshops and capture insights |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 1–2
Implementation + Onboarding | Stakeholder Alignment Workshops | Develop stakeholder map and influence matrix |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 1–2
Implementation + Onboarding | Stakeholder Alignment Workshops | Draft communication strategy and feedback cadence |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 1–2
Implementation + Onboarding | Stakeholder Alignment Workshops | Review and sign off communication plan with Steering Committee | Stakeholder Map, Communication Strategy Draft | Ensure executive and stakeholder alignment before kickoff. | CX Partner - Change Management SME | Adobe | CX Partner | 1–2
Implementation + Onboarding | Program management and coordination | Establish governance tracker and cadence calendar |  |  | Project Manager | Knapsack | Project Manager | 1–20
Implementation + Onboarding | Program management and coordination | Schedule weekly syncs and milestone reviews |  |  | Project Manager | Knapsack | Project Manager | 1–20
Implementation + Onboarding | Program management and coordination | Maintain RAID log |  |  | Project Manager | Knapsack | Project Manager | 1–20
Implementation + Onboarding | Program management and coordination | Prepare Phase 1 exit and readiness report |  |  | Project Manager | Knapsack | Project Manager | 1–20
Implementation + Onboarding | Program management and coordination | Present status updates to Adobe Steering Committee | Project Governance Tracker, Phase 1 Exit Report | Program coordination, kickoff, and phase review oversight. | Project Manager | Knapsack | Project Manager | 1–20
Implementation + Onboarding | Communication Launch Plan | Create internal messaging and visual identity kit |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 3–6
Implementation + Onboarding | Communication Launch Plan | Develop launch materials (FAQ, deck, announcement) |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 3–6
Implementation + Onboarding | Communication Launch Plan | Align with design ops for internal brand tone and channels |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 3–6
Implementation + Onboarding | Communication Launch Plan | Distribute campaign via Adobe internal comms |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 3–6
Implementation + Onboarding | Communication Launch Plan | Gather feedback and refine messaging | Internal Communication Plan, Branding Package | Launch program messaging, goals, and brand identity across teams. | CX Partner - Change Management SME | Adobe | CX Partner | 3–6
Implementation + Onboarding | Preparation | Conduct environment readiness check |  |  | Project Manager | Knapsack | Project Manager | 7–10
Implementation + Onboarding | Preparation | Validate API and endpoint configuration |  |  | Project Manager | Knapsack | Project Manager | 7–10
Implementation + Onboarding | Preparation | Verify authentication and permissions access |  |  | Project Manager | Knapsack | Project Manager | 7–10
Implementation + Onboarding | Preparation | Confirm hosting and network compliance |  |  | Project Manager | Knapsack | Project Manager | 7–10
Implementation + Onboarding | Preparation | Document results in Technical Readiness Checklist | Technical Readiness Checklist | Verify infrastructure readiness, environment setup, and permissions. | Project Manager | Knapsack | Project Manager | 7–10
Implementation + Onboarding | Local install support | Provide installation guide and validation checklist |  |  | Senior Solutions Engineer | Knapsack | Engineer | 7–10
Implementation + Onboarding | Local install support | Support local environment configuration |  |  | Senior Solutions Engineer | Knapsack | Engineer | 7–10
Implementation + Onboarding | Local install support | Troubleshoot integration issues |  |  | Senior Solutions Engineer | Knapsack | Engineer | 7–10
Implementation + Onboarding | Local install support | Validate connectivity with IPE components |  |  | Senior Solutions Engineer | Knapsack | Engineer | 7–10
Implementation + Onboarding | Local install support | Log and close install-related tickets | Installation Validation Report | Validate local environment setup for Knapsack and IPE components. | Senior Solutions Engineer | Knapsack | Engineer | 7–10
Implementation + Onboarding | Component rendering | Validate core Spectrum components rendering |  |  | Senior Solutions Engineer | Knapsack | Engineer | 7–10
Implementation + Onboarding | Component rendering | Conduct visual and functional QA across environments |  |  | Senior Solutions Engineer | Knapsack | Engineer | 7–10
Implementation + Onboarding | Component rendering | Compare results with baseline expectations |  |  | Senior Solutions Engineer | Knapsack | Engineer | 7–10
Implementation + Onboarding | Component rendering | Document rendering test summary report |  |  | Senior Solutions Engineer | Knapsack | Engineer | 7–10
Implementation + Onboarding | Component rendering | Submit remediation recommendations | Rendering QA Report | Validate successful rendering of Spectrum components across environments. | Senior Solutions Engineer | Knapsack | Engineer | 7–10
Implementation + Onboarding | SME support for rendering | Review component architecture and consistency |  |  | Subject Matter Expert | Knapsack | SME | 7–10
Implementation + Onboarding | SME support for rendering | Audit rendering pipeline and dependency mapping |  |  | Subject Matter Expert | Knapsack | SME | 7–10
Implementation + Onboarding | SME support for rendering | Validate accessibility compliance |  |  | Subject Matter Expert | Knapsack | SME | 7–10
Implementation + Onboarding | SME support for rendering | Provide expert input to engineering team |  |  | Subject Matter Expert | Knapsack | SME | 7–10
Implementation + Onboarding | SME support for rendering | Approve Architecture Validation Log | Architecture Validation Log | SME oversight of rendering logic and architectural consistency. | Subject Matter Expert | Knapsack | SME | 7–10
Implementation + Onboarding | Deployment support | Define deployment workflow and CI/CD configuration |  |  | Senior Solutions Engineer | Knapsack | Engineer | 15–20
Implementation + Onboarding | Deployment support | Create rollback and versioning process |  |  | Senior Solutions Engineer | Knapsack | Engineer | 15–20
Implementation + Onboarding | Deployment support | Run initial deployment test |  |  | Senior Solutions Engineer | Knapsack | Engineer | 15–20
Implementation + Onboarding | Deployment support | Record metrics against success criteria |  |  | Senior Solutions Engineer | Knapsack | Engineer | 15–20
Implementation + Onboarding | Deployment support | Approve Deployment Plan and Success Metrics | Deployment Plan + Success Metrics | Plan and validate deployment pipelines with measurable success criteria. | Senior Solutions Engineer | Knapsack | Engineer | 15–20
Scaled Rollout and Adoption | Program management and Steering Committee coordination | Conduct bi-weekly stand-ups with stakeholders |  |  | Project Manager | Adobe | Project Manager | 21–32
Scaled Rollout and Adoption | Program management and Steering Committee coordination | Prepare monthly summary reports |  |  | Project Manager | Adobe | Project Manager | 21–32
Scaled Rollout and Adoption | Program management and Steering Committee coordination | Track progress against milestones |  |  | Project Manager | Adobe | Project Manager | 21–32
Scaled Rollout and Adoption | Program management and Steering Committee coordination | Facilitate phase-gate review sessions |  |  | Project Manager | Adobe | Project Manager | 21–32
Scaled Rollout and Adoption | Program management and Steering Committee coordination | Update Governance Toolkit documents | Governance Toolkit + Monthly Summary Reports | Kickoff, bi-weekly stand-ups, monthly reports, phase gate reviews. | Project Manager | Adobe | Project Manager | 21–32
Scaled Rollout and Adoption | Facilitating and supporting deliverables | Collect adoption and engagement metrics |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 21–32
Scaled Rollout and Adoption | Facilitating and supporting deliverables | Populate dashboard with KPIs |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 21–32
Scaled Rollout and Adoption | Facilitating and supporting deliverables | Review metrics with CX Partner and PM |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 21–32
Scaled Rollout and Adoption | Facilitating and supporting deliverables | Recommend improvements for lagging metrics |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 21–32
Scaled Rollout and Adoption | Facilitating and supporting deliverables | Share monthly change-management insights | Change Management Dashboard | Track adoption metrics, stakeholder engagement, and training completion. | CX Partner - Change Management SME | Adobe | CX Partner | 21–32
Scaled Rollout and Adoption | Change Readiness Assessment | Draft readiness survey and baseline questions |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 21–24
Scaled Rollout and Adoption | Change Readiness Assessment | Conduct assessment sessions |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 21–24
Scaled Rollout and Adoption | Change Readiness Assessment | Analyze cultural and operational preparedness |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 21–24
Scaled Rollout and Adoption | Change Readiness Assessment | Summarize results in Readiness Index |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 21–24
Scaled Rollout and Adoption | Change Readiness Assessment | Present findings to leadership | Readiness Survey, Baseline Adoption Index | Assess cultural, technical, and operational readiness prior to implementation. | CX Partner - Change Management SME | Adobe | CX Partner | 21–24
Scaled Rollout and Adoption | FDE led Implementation + Architecture + Governance | Define system-of-systems architecture |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | FDE led Implementation + Architecture + Governance | Document governance model and accessibility plan |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | FDE led Implementation + Architecture + Governance | Review architecture with engineering leads |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | FDE led Implementation + Architecture + Governance | Finalize and publish architecture document | System of Systems Architecture Document | Define architecture, component contribution model, accessibility, governance framework. | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | Stakeholder Interviews/Workshops | Schedule interviews across departments |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | Stakeholder Interviews/Workshops | Capture key challenges and opportunities |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | Stakeholder Interviews/Workshops | Consolidate findings into themes |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | Stakeholder Interviews/Workshops | Draft recommendations report |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | Stakeholder Interviews/Workshops | Present Strategic Readout | Strategic Readout and Recommendations | Collect stakeholder inputs and align roadmap. | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | Pilot Enablement & Feedback Loop | Identify pilot groups and roles |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 23–26
Scaled Rollout and Adoption | Pilot Enablement & Feedback Loop | Conduct onboarding sessions |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 23–26
Scaled Rollout and Adoption | Pilot Enablement & Feedback Loop | Gather qualitative feedback |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 23–26
Scaled Rollout and Adoption | Pilot Enablement & Feedback Loop | Build sentiment dashboard |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 23–26
Scaled Rollout and Adoption | Pilot Enablement & Feedback Loop | Review results and refine approach | Pilot Feedback Summary, Sentiment Dashboard | Gather early adopter feedback and adjust onboarding approach. | CX Partner - Change Management SME | Adobe | CX Partner | 23–26
Scaled Rollout and Adoption | Role-Based Training Enablement | Segment audience (UX, Eng, Partners) |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 25–28
Scaled Rollout and Adoption | Role-Based Training Enablement | Develop persona-specific materials |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 25–28
Scaled Rollout and Adoption | Role-Based Training Enablement | Host training sessions |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 25–28
Scaled Rollout and Adoption | Role-Based Training Enablement | Assess comprehension via surveys |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 25–28
Scaled Rollout and Adoption | Role-Based Training Enablement | Update modules as needed | Persona-Based Training Modules (UX, Eng, Partner) | Deliver tailored enablement by persona to improve comprehension and adoption. | CX Partner - Change Management SME | Adobe | CX Partner | 25–28
Scaled Rollout and Adoption | SME support for Deployment/DevOps | Review CI/CD pipelines for readiness |  |  | Subject Matter Expert | Knapsack | SME | 21–26
Scaled Rollout and Adoption | SME support for Deployment/DevOps | Validate automation scripts |  |  | Subject Matter Expert | Knapsack | SME | 21–26
Scaled Rollout and Adoption | SME support for Deployment/DevOps | Confirm test coverage completeness |  |  | Subject Matter Expert | Knapsack | SME | 21–26
Scaled Rollout and Adoption | SME support for Deployment/DevOps | Document readiness report | DevOps Readiness | Validate CI/CD, cloud authoring, and deployment automation readiness. | Subject Matter Expert | Knapsack | SME | 21–26
Scaled Rollout and Adoption | Cloud authoring setup and testing | Configure cloud authoring environment |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Cloud authoring setup and testing | Migrate initial content set |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Cloud authoring setup and testing | Validate performance and permissions |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Cloud authoring setup and testing | Document validation results | Cloud Authoring Validation | Setup and validate authoring in cloud environments. | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | SSO setup and testing | Integrate with Adobe’s identity provider |  |  | Subject Matter Expert | Knapsack | SME | 25–28
Scaled Rollout and Adoption | SSO setup and testing | Test authentication flow and failover |  |  | Subject Matter Expert | Knapsack | SME | 25–28
Scaled Rollout and Adoption | SSO setup and testing | Validate group mapping |  |  | Subject Matter Expert | Knapsack | SME | 25–28
Scaled Rollout and Adoption | SSO setup and testing | Document SSO integration results | SSO Integration Checklist | Configure and test single sign-on with enterprise identity provider. | Subject Matter Expert | Knapsack | SME | 25–28
Scaled Rollout and Adoption | Training - Eng / UX / Partners | Develop unified curriculum |  |  | Senior Solutions Engineer | Adobe | Engineer | 29–32
Scaled Rollout and Adoption | Training - Eng / UX / Partners | Schedule and deliver training |  |  | Senior Solutions Engineer | Adobe | Engineer | 29–32
Scaled Rollout and Adoption | Training - Eng / UX / Partners | Track attendance and feedback |  |  | Senior Solutions Engineer | Adobe | Engineer | 29–32
Scaled Rollout and Adoption | Training - Eng / UX / Partners | Refine enablement materials | Unified Enablement Curriculum | Integrated training for engineering, UX, and partner audiences. | Senior Solutions Engineer | Adobe | Engineer | 29–32
Scaled Rollout and Adoption | Workflow Diagrams | Document self-service and contribution workflows |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | Workflow Diagrams | Create FigJam diagrams |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | Workflow Diagrams | Review with design ops and engineering |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | Workflow Diagrams | Publish workflow package | Workflow Documentation (FigJam, Token Studio, Contribution Workflows) | Map self-service contribution and implementation workflows. | Senior Solutions Engineer | Knapsack | Engineer | 21–24
Scaled Rollout and Adoption | Content planning and integration | Map documentation inventory |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Content planning and integration | Create cross-platform implementation guides |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Content planning and integration | Validate completeness and consistency |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Content planning and integration | Publish documentation set | Multi-platform Implementation Guides | Documentation for web, React, iOS, Android implementations. | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Advanced Training - Partners + Contribution | Identify advanced partner cohort |  |  | Senior Solutions Engineer | Adobe | Engineer | 29–32
Scaled Rollout and Adoption | Advanced Training - Partners + Contribution | Deliver deep-dive workshops |  |  | Senior Solutions Engineer | Adobe | Engineer | 29–32
Scaled Rollout and Adoption | Advanced Training - Partners + Contribution | Assess capability maturity |  |  | Senior Solutions Engineer | Adobe | Engineer | 29–32
Scaled Rollout and Adoption | Advanced Training - Partners + Contribution | Recognize high-performing contributors | Advanced Enablement Program | Deep-dive enablement for partner contributions. | Senior Solutions Engineer | Adobe | Engineer | 29–32
Scaled Rollout and Adoption | Phase Gate Strategic Recommendations + Documentation | Review milestone progress |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–32
Scaled Rollout and Adoption | Phase Gate Strategic Recommendations + Documentation | Conduct readiness evaluation |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–32
Scaled Rollout and Adoption | Phase Gate Strategic Recommendations + Documentation | Document lessons learned |  |  | Senior Solutions Engineer | Knapsack | Engineer | 21–32
Scaled Rollout and Adoption | Phase Gate Strategic Recommendations + Documentation | Prepare scale-up recommendations | Scaled Rollout Readiness Review | Formal phase gate review and recommendations. | Senior Solutions Engineer | Knapsack | Engineer | 21–32
Scaled Rollout and Adoption | Pre-Cutover Readiness Review | Verify technical and operational prerequisites |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Pre-Cutover Readiness Review | Conduct dry-run deployment |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Pre-Cutover Readiness Review | Validate SSO and environment stability |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Pre-Cutover Readiness Review | Approve readiness sign-off | Cutover Readiness Checklist, Technical Validation Sign-off, Risk Mitigation Plan | Validate all technical, operational, and training prerequisites; confirm SSO, component rendering, deployment readiness before final rollout. | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Data & Configuration Freeze | Lock repositories and configuration files |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Data & Configuration Freeze | Capture environment snapshot |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Data & Configuration Freeze | Validate rollback plan |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Data & Configuration Freeze | Communicate freeze timeline | Configuration Freeze Log, Environment Snapshot | Lock configuration and repositories; capture environment snapshot for rollback if needed before go-live. | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Final UAT & Stakeholder Acceptance | Develop UAT scripts |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Final UAT & Stakeholder Acceptance | Facilitate sessions with pilot users |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Final UAT & Stakeholder Acceptance | Log and triage issues |  |  | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Final UAT & Stakeholder Acceptance | Capture sign-off from business owners | UAT Sign-off Report, Known Issues Log | Conduct final user acceptance testing with pilot teams; log and triage known issues before launch. | Senior Solutions Engineer | Knapsack | Engineer | 25–28
Scaled Rollout and Adoption | Change Impact Analysis | Identify impacted teams |  |  | CX Partner - Change Management SME | Knapsack | CX Partner | 21–24
Scaled Rollout and Adoption | Change Impact Analysis | Conduct stakeholder interviews |  |  | CX Partner - Change Management SME | Knapsack | CX Partner | 21–24
Scaled Rollout and Adoption | Change Impact Analysis | Document change action plans |  |  | CX Partner - Change Management SME | Knapsack | CX Partner | 21–24
Scaled Rollout and Adoption | Change Impact Analysis | Share mitigation strategies | Change Impact Log, Stakeholder Action Plan | Evaluate and manage business unit impacts during scale-up. | CX Partner - Change Management SME | Knapsack | CX Partner | 21–24
Scaled Rollout and Adoption | Adoption Acceleration Campaign | Develop success-story series |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 29–32
Scaled Rollout and Adoption | Adoption Acceleration Campaign | Publish awareness materials |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 29–32
Scaled Rollout and Adoption | Adoption Acceleration Campaign | Monitor engagement analytics |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 29–32
Scaled Rollout and Adoption | Adoption Acceleration Campaign | Share outcomes in adoption dashboard | Awareness Campaign, Success Story Series | Promote awareness and highlight early success stories to drive adoption. | CX Partner - Change Management SME | Adobe | CX Partner | 29–32
Scaled Rollout and Adoption | Partner Enablement & Recognition | Define contribution metrics |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 29–32
Scaled Rollout and Adoption | Partner Enablement & Recognition | Build leaderboard dashboard |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 29–32
Scaled Rollout and Adoption | Partner Enablement & Recognition | Communicate recognition framework |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 29–32
Scaled Rollout and Adoption | Partner Enablement & Recognition | Host partner recognition event | Partner Contribution Leaderboard, Recognition Plan | Drive engagement through recognition and contribution metrics. | CX Partner - Change Management SME | Adobe | CX Partner | 29–32
Optimization and Continued Support | Transition support | Conduct lessons-learned session |  |  | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Transition support | Update improvement backlog |  |  | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Transition support | Create continuous improvement plan |  |  | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Transition support | Share analytics summary | Continuous Improvement Plan | Continuous improvement plan with analytics and recommendations. | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Cutover Execution | Perform production deployment |  |  | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Cutover Execution | Validate access and permissions |  |  | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Cutover Execution | Monitor service health dashboard |  |  | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Cutover Execution | Confirm deployment sign-off | Deployment Completion Report, Access Validation, Service Health Dashboard | Execute production deployment; validate access controls, deployment integrity, and service health. | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Go-Live Communication Launch | Draft go-live announcement and FAQ |  |  | Project Manager | Adobe | Project Manager | 33+
Optimization and Continued Support | Go-Live Communication Launch | Coordinate internal distribution |  |  | Project Manager | Adobe | Project Manager | 33+
Optimization and Continued Support | Go-Live Communication Launch | Activate support channels |  |  | Project Manager | Adobe | Project Manager | 33+
Optimization and Continued Support | Go-Live Communication Launch | Collect user questions for knowledge base | Internal Announcement, Go-Live FAQ, Support Channels | Announce official go-live to stakeholders; provide communication templates and support channels. | Project Manager | Adobe | Project Manager | 33+
Optimization and Continued Support | Hypercare Phase (Post-Go-Live Support) | Provide high-touch post-launch support |  |  | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Hypercare Phase (Post-Go-Live Support) | Monitor tickets and SLAs |  |  | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Hypercare Phase (Post-Go-Live Support) | Resolve critical issues |  |  | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Hypercare Phase (Post-Go-Live Support) | Deliver weekly hypercare reports | Hypercare Status Reports, Issue Resolution Tracker | Provide high-touch support for 30–90 days post go-live, track SLAs, and stabilize the system. | Senior Solutions Engineer | Knapsack | Engineer | 33+
Optimization and Continued Support | Post-Implementation Review | Analyze KPIs and satisfaction metrics |  |  | Project Manager | Adobe | Project Manager | 33+
Optimization and Continued Support | Post-Implementation Review | Conduct stakeholder debrief |  |  | Project Manager | Adobe | Project Manager | 33+
Optimization and Continued Support | Post-Implementation Review | Document lessons learned |  |  | Project Manager | Adobe | Project Manager | 33+
Optimization and Continued Support | Post-Implementation Review | Prepare optimization backlog | Lessons Learned Summary, KPI Report, Optimization Backlog | Evaluate performance, adoption, and partner satisfaction to inform optimization roadmap. | Project Manager | Adobe | Project Manager | 33+
Optimization and Continued Support | Transition to Steady-State Operations | Facilitate knowledge transfer sessions |  |  | Design System Lead | Adobe | Design Lead | 33+
Optimization and Continued Support | Transition to Steady-State Operations | Deliver ownership matrix |  |  | Design System Lead | Adobe | Design Lead | 33+
Optimization and Continued Support | Transition to Steady-State Operations | Confirm governance cadence |  |  | Design System Lead | Adobe | Design Lead | 33+
Optimization and Continued Support | Transition to Steady-State Operations | Transition documentation to internal owners | Knowledge Transfer Documentation, Ownership Matrix, Future Roadmap | Transition ownership to internal design ops and engineering teams; confirm governance cadence. | Design System Lead | Adobe | Design Lead | 33+
Optimization and Continued Support | Continuous Improvement Framework | Develop sentiment tracking dashboards |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 33+
Optimization and Continued Support | Continuous Improvement Framework | Monitor adoption trends |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 33+
Optimization and Continued Support | Continuous Improvement Framework | Recommend process improvements |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 33+
Optimization and Continued Support | Continuous Improvement Framework | Report quarterly metrics | Adoption Dashboards, Sentiment Trend Reports | Maintain engagement and track long-term adoption trends. | CX Partner - Change Management SME | Adobe | CX Partner | 33+
Optimization and Continued Support | Strategic Partnership Review | Conduct quarterly business reviews |  |  | CX Partner - Change Management SME | Knapsack | CX Partner | 33+
Optimization and Continued Support | Strategic Partnership Review | Analyze partnership performance |  |  | CX Partner - Change Management SME | Knapsack | CX Partner | 33+
Optimization and Continued Support | Strategic Partnership Review | Identify collaboration opportunities |  |  | CX Partner - Change Management SME | Knapsack | CX Partner | 33+
Optimization and Continued Support | Strategic Partnership Review | Update partnership roadmap | Quarterly Business Review Deck | Evaluate ongoing partnership alignment and strategic direction. | CX Partner - Change Management SME | Knapsack | CX Partner | 33+
Optimization and Continued Support | Case Study Development | Collect success metrics and outcomes |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 33+
Optimization and Continued Support | Case Study Development | Draft internal case study |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 33+
Optimization and Continued Support | Case Study Development | Obtain approvals for publishing |  |  | CX Partner - Change Management SME | Adobe | CX Partner | 33+
Optimization and Continued Support | Case Study Development | Archive case study in program library | Internal Case Study + Success Metrics | Document program success and outcomes for future scaling. | CX Partner - Change Management SME | Adobe | CX Partner | 33+
Implementation + Onboarding | Design System Charter & Reference Architecture | Define design system scope, tiering (core vs product), and success metrics (JTBD + KPIs) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 2–3
Implementation + Onboarding | Design System Charter & Reference Architecture | Align stakeholders on governance model (decision rights, contribution, release ownership) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 2–3
Implementation + Onboarding | Design System Charter & Reference Architecture | Draft reference architecture (tokens → packages → docs → integrations) and data flows |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 2–3
Implementation + Onboarding | Design System Charter & Reference Architecture | Define adoption measurement plan (usage, drift, quality, velocity) and instrumentation points |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 2–3
Implementation + Onboarding | Design System Charter & Reference Architecture | Finalize charter and publish operating cadence | Design System Charter + Reference Architecture | Charter, KPIs, governance, and reference architecture diagram for the design↔code system. | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 2–3
Implementation + Onboarding | Foundations & Token Taxonomy | Audit existing foundations (color/type/spacing/elevation/motion/icons) and define target standards |  |  | Knapsack - Design System Lead | Knapsack | Design Lead | 3–4
Implementation + Onboarding | Foundations & Token Taxonomy | Define token taxonomy (global/semantic/component) and naming conventions |  |  | Knapsack - Design System Lead | Knapsack | Design Lead | 3–4
Implementation + Onboarding | Foundations & Token Taxonomy | Define theming model (brand themes, dark mode, high contrast) and constraints |  |  | Knapsack - Design System Lead | Knapsack | Design Lead | 3–4
Implementation + Onboarding | Foundations & Token Taxonomy | Define content and accessibility guidelines for foundations (contrast, typography, motion) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 3–4
Implementation + Onboarding | Foundations & Token Taxonomy | Create token governance rules (who can change what, versioning, approvals) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 3–4
Implementation + Onboarding | Foundations & Token Taxonomy | Publish foundations + token spec in design + docs | Foundations + Token Specification | Foundations standards and token taxonomy/naming/theming/governance guidance. | Knapsack - Design System Lead | Knapsack | Design Lead | 3–4
Implementation + Onboarding | Token Pipeline Build & Theming Strategy | Select/confirm token tooling and define source of truth (design vs repo) rules |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Implementation + Onboarding | Token Pipeline Build & Theming Strategy | Implement token export/build pipeline (validation, transforms, outputs) |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–6
Implementation + Onboarding | Token Pipeline Build & Theming Strategy | Generate platform outputs (web JSON/CSS vars; add others if needed) and verify integrity |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–6
Implementation + Onboarding | Token Pipeline Build & Theming Strategy | Implement theme packaging and switching strategy (e.g., multiple brands / modes) |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–6
Implementation + Onboarding | Token Pipeline Build & Theming Strategy | Set up CI checks for token schema validation and breaking-change detection |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–6
Implementation + Onboarding | Token Pipeline Build & Theming Strategy | Document token contribution + release workflow | Token Pipeline + Theme Artifacts | Automated token build outputs, theming strategy, CI validation, and contribution workflow. | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Implementation + Onboarding | Component Inventory & Prioritization | Inventory existing components and map to user journeys / product surfaces |  |  | Knapsack - Design System Lead | Knapsack | Design Lead | 2–3
Implementation + Onboarding | Component Inventory & Prioritization | Define component maturity levels and acceptance criteria (spec completeness, a11y, tests) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 2–3
Implementation + Onboarding | Component Inventory & Prioritization | Prioritize MVP component set and create backlog with sequencing |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 2–3
Implementation + Onboarding | Component Inventory & Prioritization | Define component spec template (anatomy, states, content rules, accessibility, tokens) |  |  | Knapsack - Design System Lead | Knapsack | Design Lead | 2–3
Implementation + Onboarding | Component Inventory & Prioritization | Publish component roadmap and MVP scope | Component Inventory + MVP Roadmap | Inventory, prioritization matrix, MVP scope, and backlog sequencing. | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 2–3
Implementation + Onboarding | Component API Standards & Templates | Define component API patterns (props, composition, slots, variants) and naming conventions |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–4
Implementation + Onboarding | Component API Standards & Templates | Define accessibility patterns per component type (keyboard, focus, ARIA, semantics) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 3–4
Implementation + Onboarding | Component API Standards & Templates | Create starter templates for component implementation and tests |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–4
Implementation + Onboarding | Component API Standards & Templates | Define contribution workflow (RFC, review gates, required artifacts) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 3–4
Implementation + Onboarding | Component API Standards & Templates | Publish standards in docs and align with code owners | Component Standards + Contribution Model | Component API standards, a11y patterns, templates, and contribution/review workflow. | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–4
Implementation + Onboarding | Code Connect Strategy & Configuration | Define Code Connect coverage targets and connected-component definition (source of truth) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 2–4
Implementation + Onboarding | Code Connect Strategy & Configuration | Set up Code Connect configuration and repo/package references |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 2–4
Implementation + Onboarding | Code Connect Strategy & Configuration | Define mapping conventions (component IDs, variants/states, props) and ownership model |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 2–4
Implementation + Onboarding | Code Connect Strategy & Configuration | Implement initial mappings for MVP components and verify accuracy |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 2–4
Implementation + Onboarding | Code Connect Strategy & Configuration | Define drift detection + remediation workflow (design↔code mismatch) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 2–4
Implementation + Onboarding | Code Connect Strategy & Configuration | Publish Code Connect playbook and governance | Code Connect Setup + Drift Governance | Connected component strategy, configuration, mapping conventions, and drift SOP. | Knapsack - Design System / Platform SME | Knapsack | SME | 2–4
Implementation + Onboarding | Documentation IA & Templates (Design System Docs) | Define docs information architecture (Foundations, Tokens, Components, Patterns, Content, A11y) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 2–3
Implementation + Onboarding | Documentation IA & Templates (Design System Docs) | Create docs templates (component pages, token pages, pattern pages, migration guides) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 2–3
Implementation + Onboarding | Documentation IA & Templates (Design System Docs) | Set up docs site scaffold and navigation (or align existing docs site) |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 2–3
Implementation + Onboarding | Documentation IA & Templates (Design System Docs) | Create “Getting Started” guides for designers, engineers, and partners |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 2–3
Implementation + Onboarding | Documentation IA & Templates (Design System Docs) | Publish initial docs structure and ownership/freshness rules | Design System Documentation IA + Templates | Docs structure, page templates, and ownership/freshness model for living documentation. | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 2–3
Implementation + Onboarding | Quality Gates Setup (A11y, Visual, Performance, Security) | Define quality gate policy (release criteria for components/tokens/docs) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 3–5
Implementation + Onboarding | Quality Gates Setup (A11y, Visual, Performance, Security) | Set up accessibility automation (linting, test utilities, checks) and manual audit process |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–5
Implementation + Onboarding | Quality Gates Setup (A11y, Visual, Performance, Security) | Set up visual regression testing and baseline snapshot workflow |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–5
Implementation + Onboarding | Quality Gates Setup (A11y, Visual, Performance, Security) | Define performance budgets for components and measurement approach |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–5
Implementation + Onboarding | Quality Gates Setup (A11y, Visual, Performance, Security) | Review secure publishing pipeline (dependency policy, provenance/signing if applicable) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 3–5
Implementation + Onboarding | Quality Gates Setup (A11y, Visual, Performance, Security) | Publish QA checklist and integrate gates into CI/CD | Quality Gates + Automation Framework | Automated quality checks (a11y/visual/perf/security) and release gating policy. | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–5
Implementation + Onboarding | Release Engineering & Package Strategy | Define repo strategy (mono/polyrepo) and package boundaries |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–5
Implementation + Onboarding | Release Engineering & Package Strategy | Define semantic versioning, changelog, and release notes standards |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 3–5
Implementation + Onboarding | Release Engineering & Package Strategy | Implement CI/CD for build/test/publish packages and deploy docs |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–5
Implementation + Onboarding | Release Engineering & Package Strategy | Set up compatibility testing (breaking changes, supported versions matrix) |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–5
Implementation + Onboarding | Release Engineering & Package Strategy | Define deprecation and migration policy (sunset timelines, migration guides) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 3–5
Implementation + Onboarding | Release Engineering & Package Strategy | Publish release playbook and ownership | Release Playbook + CI/CD Pipelines | Package strategy, semver/release standards, CI/CD pipelines, and compatibility policy. | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 3–5
Implementation + Onboarding | AI Contextual Capabilities – Context Model & Knowledge Base | Define AI JTBD and supported user journeys (recommend, explain, generate safely, lint) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Implementation + Onboarding | AI Contextual Capabilities – Context Model & Knowledge Base | Define context schema/ontology (product, platform, theme, constraints, persona) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Implementation + Onboarding | AI Contextual Capabilities – Context Model & Knowledge Base | Curate knowledge sources (docs, tokens, component specs, governance rules) and ownership |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Implementation + Onboarding | AI Contextual Capabilities – Context Model & Knowledge Base | Implement retrieval/indexing approach (metadata/tags + search/index; freshness rules) |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–6
Implementation + Onboarding | AI Contextual Capabilities – Context Model & Knowledge Base | Define prompt patterns and response formats tied to system entities (tokens/components/patterns) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Implementation + Onboarding | AI Contextual Capabilities – Context Model & Knowledge Base | Establish human-in-the-loop review and escalation paths for risky outputs |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 4–6
Implementation + Onboarding | AI Contextual Capabilities – Context Model & Knowledge Base | Publish AI context design and operations plan | AI Context Model + Knowledge Base Plan | Context schema, curated sources, retrieval approach, prompt patterns, and governance plan. | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Scaled Rollout and Adoption | Component Library MVP Build (Core Set) | Implement MVP component set in code (per roadmap) with tokens wired-in |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 6–10
Scaled Rollout and Adoption | Component Library MVP Build (Core Set) | Create component tests (unit/integration) and a11y coverage per standards |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 6–10
Scaled Rollout and Adoption | Component Library MVP Build (Core Set) | Build usage examples and recipes for each MVP component |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 6–10
Scaled Rollout and Adoption | Component Library MVP Build (Core Set) | Run design↔code alignment review (spec conformance, states, variants) |  |  | Knapsack - Design System Lead | Knapsack | Design Lead | 6–10
Scaled Rollout and Adoption | Component Library MVP Build (Core Set) | Publish packages and docs for MVP components |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 6–10
Scaled Rollout and Adoption | Component Library MVP Build (Core Set) | Pilot adoption with 1–2 product teams and collect issues |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 6–10
Scaled Rollout and Adoption | Component Library MVP Build (Core Set) | Refine based on pilot feedback and finalize MVP release | MVP Component Library Release | Published component packages + docs + examples for the MVP set, validated by pilot teams. | Knapsack - Design Systems Engineer | Knapsack | Engineer | 6–10
Scaled Rollout and Adoption | Code Connect Coverage Expansion & Drift Remediation | Expand Code Connect mappings to additional high-value components |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–6
Scaled Rollout and Adoption | Code Connect Coverage Expansion & Drift Remediation | Validate mappings across variants/states and align naming/props |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–6
Scaled Rollout and Adoption | Code Connect Coverage Expansion & Drift Remediation | Establish drift reporting (coverage, freshness, mismatch categories) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Scaled Rollout and Adoption | Code Connect Coverage Expansion & Drift Remediation | Run drift remediation cycles with code/design owners |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 4–6
Scaled Rollout and Adoption | Code Connect Coverage Expansion & Drift Remediation | Document common drift patterns and prevention guidance |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Scaled Rollout and Adoption | Code Connect Coverage Expansion & Drift Remediation | Publish connected coverage dashboard and SOP | Code Connect Coverage + Drift Dashboard | Expanded connected coverage with drift reporting, remediation workflow, and dashboards. | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–6
Scaled Rollout and Adoption | Docs Launch + Recipes & Migration Guides | Publish foundations, tokens, and component standards in docs site |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 3–5
Scaled Rollout and Adoption | Docs Launch + Recipes & Migration Guides | Publish recipes/patterns library (common flows, layouts, accessibility patterns) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 3–5
Scaled Rollout and Adoption | Docs Launch + Recipes & Migration Guides | Create migration guides for adopting new packages/components (including deprecations) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 3–5
Scaled Rollout and Adoption | Docs Launch + Recipes & Migration Guides | Add embedded code samples and playground links (governed snippet sources) |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–5
Scaled Rollout and Adoption | Docs Launch + Recipes & Migration Guides | Launch docs and establish update cadence + ownership model | Design System Docs v1 Launch | Published docs with recipes, migration guides, governed snippets, and ownership cadence. | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 3–5
Scaled Rollout and Adoption | Partner Contribution Pathway & Certification | Define partner contribution workflow (intake, sandbox, review gates, SLAs) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 3–5
Scaled Rollout and Adoption | Partner Contribution Pathway & Certification | Create partner contribution kit (templates, checklists, example PRs) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 3–5
Scaled Rollout and Adoption | Partner Contribution Pathway & Certification | Define certification rubric (design + code + a11y + tests + documentation) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 3–5
Scaled Rollout and Adoption | Partner Contribution Pathway & Certification | Implement badges/labels for certified components/patterns in docs |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 3–5
Scaled Rollout and Adoption | Partner Contribution Pathway & Certification | Pilot partner contribution with 1 partner and iterate workflow |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 3–5
Scaled Rollout and Adoption | Partner Contribution Pathway & Certification | Launch partner pathway program and publish certification criteria | Partner Contribution + Certification Program | Partner workflow, certification rubric, and publishing mechanics for approved contributions. | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 3–5
Scaled Rollout and Adoption | AI Contextual Capabilities – Workflow Integrations | Design AI assistant experiences for designers (Figma) and engineers (docs/IDE) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 4–8
Scaled Rollout and Adoption | AI Contextual Capabilities – Workflow Integrations | Implement Figma-side entry point (plugin/UI) for contextual recommendations and linting |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–8
Scaled Rollout and Adoption | AI Contextual Capabilities – Workflow Integrations | Implement docs-site assistant for contextual guidance and search/Q&A |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–8
Scaled Rollout and Adoption | AI Contextual Capabilities – Workflow Integrations | Implement IDE/PR assistant hooks (optional) for component/token guidance and compliance |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–8
Scaled Rollout and Adoption | AI Contextual Capabilities – Workflow Integrations | Add human approval flow for risky actions (generation, large refactors) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 4–8
Scaled Rollout and Adoption | AI Contextual Capabilities – Workflow Integrations | Pilot integrations with selected teams and capture feedback | AI Workflow Integrations MVP | Initial AI integration points (Figma/docs/IDE as applicable) piloted with teams. | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 4–8
Scaled Rollout and Adoption | AI Contextual Capabilities – Evaluation Harness + Telemetry | Define evaluation metrics (accuracy, policy compliance, latency, satisfaction) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Scaled Rollout and Adoption | AI Contextual Capabilities – Evaluation Harness + Telemetry | Create golden test set (prompts + expected outcomes) based on real workflows |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Scaled Rollout and Adoption | AI Contextual Capabilities – Evaluation Harness + Telemetry | Implement automated evaluation harness and regression checks |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–6
Scaled Rollout and Adoption | AI Contextual Capabilities – Evaluation Harness + Telemetry | Instrument telemetry (queries, acceptance, edits, failures, drift incidents) |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | 4–6
Scaled Rollout and Adoption | AI Contextual Capabilities – Evaluation Harness + Telemetry | Set up dashboards and feedback triage workflow |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | 4–6
Scaled Rollout and Adoption | AI Contextual Capabilities – Evaluation Harness + Telemetry | Run first eval cycle and iterate prompts/retrieval based on results | AI Evaluation + Telemetry Dashboard | Automated eval suite and telemetry dashboards with a triage/iteration workflow. | Knapsack - Design System / Platform SME | Knapsack | SME | 4–6
Optimization and Continued Support | Continuous Quality & Accessibility Automation | Maintain and expand a11y and visual regression baselines as components grow |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | Ongoing
Optimization and Continued Support | Continuous Quality & Accessibility Automation | Perform periodic audits (a11y, performance) and track remediation backlog |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | Ongoing
Optimization and Continued Support | Continuous Quality & Accessibility Automation | Add new quality gates based on incident learnings and drift patterns |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | Ongoing
Optimization and Continued Support | Continuous Quality & Accessibility Automation | Publish quarterly quality report (issues, fixes, risk areas) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | Ongoing
Optimization and Continued Support | Continuous Quality & Accessibility Automation | Refine QA playbooks and contributor checklists | Quarterly Quality + A11y Report | Ongoing quality automation upkeep with periodic reporting and remediation tracking. | Knapsack - Design System / Platform SME | Knapsack | SME | Ongoing
Optimization and Continued Support | Release Cadence, Deprecations & Migrations | Run regular release cadence (monthly/quarterly) with changelog automation |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | Ongoing
Optimization and Continued Support | Release Cadence, Deprecations & Migrations | Execute deprecations per policy and maintain migration guides |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | Ongoing
Optimization and Continued Support | Release Cadence, Deprecations & Migrations | Support teams through upgrades (office hours, PR assistance, issue triage) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | Ongoing
Optimization and Continued Support | Release Cadence, Deprecations & Migrations | Monitor compatibility and fix regressions quickly |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | Ongoing
Optimization and Continued Support | Release Cadence, Deprecations & Migrations | Publish release communications and adoption notes | Release Cadence + Migration Program | Defined cadence with deprecation/migration support and consistent release communications. | Knapsack - Program/Delivery PM | Knapsack | Project Manager | Ongoing
Optimization and Continued Support | Adoption Analytics & Reporting (Design↔Code) | Instrument usage analytics (package installs, component usage, token usage) where possible |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | Ongoing
Optimization and Continued Support | Adoption Analytics & Reporting (Design↔Code) | Define adoption KPIs and reporting views per persona (design, eng, leadership) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | Ongoing
Optimization and Continued Support | Adoption Analytics & Reporting (Design↔Code) | Publish monthly adoption report and insights (hotspots, gaps, drift) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | Ongoing
Optimization and Continued Support | Adoption Analytics & Reporting (Design↔Code) | Maintain backlog of adoption friction and prioritize fixes | Adoption Analytics Dashboard + Monthly Report | Ongoing analytics and reporting across design↔code adoption and system health. | Knapsack - Program/Delivery PM | Knapsack | Project Manager | Ongoing
Optimization and Continued Support | AI Contextual Capabilities – Guardrails, Governance & Iteration | Implement/maintain guardrails (allowed actions, policy filters, safe defaults) |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | Ongoing
Optimization and Continued Support | AI Contextual Capabilities – Guardrails, Governance & Iteration | Define AI governance board/cadence (changes, incident response, approvals) |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | Ongoing
Optimization and Continued Support | AI Contextual Capabilities – Guardrails, Governance & Iteration | Run regular eval + telemetry reviews and prioritize improvements |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | Ongoing
Optimization and Continued Support | AI Contextual Capabilities – Guardrails, Governance & Iteration | Improve retrieval quality (metadata, freshness, coverage) and reduce hallucinations |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | Ongoing
Optimization and Continued Support | AI Contextual Capabilities – Guardrails, Governance & Iteration | Document AI change log and communicate capability updates |  |  | Knapsack - Program/Delivery PM | Knapsack | Project Manager | Ongoing
Optimization and Continued Support | AI Contextual Capabilities – Guardrails, Governance & Iteration | Conduct periodic privacy/security review for AI integrations and data handling | AI Governance + Guardrails Program | Ongoing guardrails, governance cadence, eval/telemetry reviews, and privacy/security checks. | Knapsack - Design System / Platform SME | Knapsack | SME | Ongoing
Optimization and Continued Support | AI Contextual Capabilities – Feedback Loop + Knowledge Refresh | Triage user feedback and tag gaps (missing docs, components, patterns) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | Ongoing
Optimization and Continued Support | AI Contextual Capabilities – Feedback Loop + Knowledge Refresh | Refresh knowledge base and prompts when system changes (tokens/components/releases) |  |  | Knapsack - Design Systems Engineer | Knapsack | Engineer | Ongoing
Optimization and Continued Support | AI Contextual Capabilities – Feedback Loop + Knowledge Refresh | Measure impact of improvements (acceptance rate, reduced support tickets) |  |  | Knapsack - Design System / Platform SME | Knapsack | SME | Ongoing
Optimization and Continued Support | AI Contextual Capabilities – Feedback Loop + Knowledge Refresh | Publish quarterly AI capability maturity update | Quarterly AI Context Refresh + Impact Report | Feedback-driven updates to knowledge/prompting with measured impact reporting. | Knapsack - Program/Delivery PM | Knapsack | Project Manager | Ongoing

## Proposed Solution - CX + FDE En
Rollup | Item | Milestone Deliverables | Total Cost
Role | Adobe
Role | Forward Deployed Engineer
Role | Subject Matter Experts
Role | CX Partner - Change Management SME
One Time Implementation Fee |  |  | 58380
Annual Licensing Fee |  |  | 250000
Non-Subscription Price
Rollup | Item | Count of Milestone Deliverables | Total Cost
Role | Adobe
Role | Forward Deployed Engineer
Role | Subject Matter Experts
One Time Implementation Fee |  |  | 58380
Annual Licensing Fee |  |  | 250000
Non-Subscription Price
Rollup | Item | Count of Milestone Deliverables | Total Cost
Role | Project Manager |  | 18720
Role | Forward Deployed Engineer |  | 220220
Role | CX Partner - Change Management SME |  | 187200
Role | Subject Matter Experts - included in ProServices Subscription |  | 0
One Time Implementation Fee |  |  | 58380
Annual Licensing Fees |  |  | 250000
Non-Subscription Price
Total Year 1 Software and Implementation + Pro Services
Discount 15% for ProServices Subscription
Discounted Total Year 1 Software and Implementation + Pro Services

## Proposed Solution with CX Coach
Rollup | Item | Milestone Deliverables | Total Cost | Total Hours
Role | Adobe
Role | Forward Deployed Engineer
Role | Subject Matter Experts
Role | CX Partner - Change Management + Coaching for Adobe Team
One Time Implementation Fee |  |  | 58380
Annual Licensing Fee |  |  | 250000
Non-Subscription Price
Rollup | Item | Count of Milestone Deliverables | Total Cost | Total Hours
Role | Adobe
Role | Forward Deployed Engineer
Role | Subject Matter Experts
One Time Implementation Fee |  |  | 58380
Annual Licensing Fee |  |  | 250000
Non-Subscription Price
Rollup | Item | Count of Milestone Deliverables | Total Cost | Total Hours
Role | Project Manager |  | 18720 | 104
Role | Forward Deployed Engineer |  | 220220 | 911
Role | CX Partner - Change Management SME |  | 187200 | 362
Role | Subject Matter Experts - included in ProServices Subscription |  | 0
One Time Implementation Fee |  |  | 58380
Annual Licensing Fees |  |  | 250000
Non-Subscription Price
Total Year 1 Software and Implementation + Pro Services
Discount 15% for ProServcies Subscription
Discounted Total Year 1 Software and Implementation + Pro Services

## Proposed Solution Without CX Pa
Rollup | Item | Milestone Deliverables | Total Cost | Total Hours
Role | Adobe
Role | Forward Deployed Engineer
Role | Subject Matter Experts
Role | CX Partner - Change Management SME |  |  | 59
One Time Implementation Fee |  |  | 58380
Annual Licensing Fee |  |  | 250000
Non-Subscription Price
Rollup | Item | Count of Milestone Deliverables | Total Cost | Total Hours
Role | Adobe
Role | Forward Deployed Engineer
Role | Subject Matter Experts
One Time Implementation Fee |  |  | 58380
Annual Licensing Fee |  |  | 250000
Non-Subscription Price
Rollup | Item | Count of Milestone Deliverables | Total Cost | Total Hours
Role | Project Manager |  | 18720 | 104
Role | Forward Deployed Engineer |  | 220220 | 911
Role | CX Partner - Change Management SME |  | 187200 | 362
Role | Subject Matter Experts - included in ProServices Subscription |  | 0
One Time Implementation Fee |  |  | 58380
Annual Licensing Fees |  |  | 250000
Non-Subscription Price
Total Year 1 Software and Implementation + Pro Services
Discount 15% for ProServcies Subscription
Discounted Total Year 1 Software and Implementation + Pro Services

## Instructions - Internal (hidden)
Adobe Resource Planning Model v2.0 — How to:
1) Milestones: Review/adjust phases, activities, dates. (Source of truth)
2) Lookups - Rates: Confirm Vendor/Role rates. (Procurement-owned)
3) Lookups - Complexity: Set hours by Low/Medium/High for tasks.
4) Plan: Pick Milestone, Vendor, Role, Effort Type (Hours/Days/FTE) & Complexity.
- Hours auto-calc from Complexity when selected; can be overridden.
- Costs derive from Rate Card and Assumptions.
5) TimePhasing: Hours & costs spread by month from Start to End dates.
6) Summary: Rollups by Vendor, Role, Phase for executive review.

## Rate Card
Rate Card
Knapsack ProServices Resource | Rate | Complexity Rating from Assessment | Approxiamate FTE Utilization | Approxiamate Hours | Resource Justification | Additional Notes
Senior Solutions Engineer | 220 | High - high impact score, high impact score | 30% |  | Implementation + Architecture + Governance scope and lacking a dedicated engineering resource requires a Forward Deployed Engineer to derisk and accelerate time to value for Adobe Users | Knapsack will provide this resource as part of the subscription offering
CX Partner | 300 | High - high impact score, high impact score | 20% |  | Spectrum 2 Migration requirement, shift to a multi-platform delivery model, Implementation Partner Network scale, Users in Scope, and Change Management Scope requires a CX Partner Engaged | Knapsack will provide this resource as part of the subscription offering
Knapsack T&M Contract Resource | Rate | Complexity Rating from Assessment | Approxiamate FTE Utilization | Actual Hours | Resource Justification | Additional Notes
Project Manager | 180 | Medium - high impact score, low complexity score | 5% |  | Steering Committee required for implementations with a High Level of complexity and given the Change Management scope required to de-risk the Spectrum 2 Migration and enablement of Implementation Partners | Knapsack will provide this resource as a part of the subscription offering for 120 hours
Subject Matter Expert | 500 | High - high impact score, high impact score - enhancements in scope | 5% |  | Complex Cloud Authoring requirements scope required to support the volume of users and enterprise security requirements | Knapsack will provide this resource as a part of the subscription offering for 40 hours
Product Engineer | 400 | High - high impact score, high impact score - enhancements in scope | 5% |  | Some enhancements may be required to support the desired multi-platform delivery requirements and self-serve workflows | Knapsack will provide this resource as a part of the subscription offering for 40 hours
Contractor Resources |  |  |  |  | If requirements are discovered that are outside of the current scope of work - a specialized resource may be required and Knapsack will support carrying that resource on our paper and will manage the delivery if required | Knapsack will support retaining contractor resources as needed at a 15% mark up

## Milestones (hidden)
Phase | Activity | Deliverable | Description | Knapsack Role Description | Start Date | End Date | Accountable Party
Scaled Rollout and Adoption | Program management and Steering Committee coordination | Governance Toolkit + Monthly Summary Reports | Kickoff, bi-weekly stand-ups, monthly reports, phase gate reviews | Project Manager | 2025-12-01 | 2026-11-30 | Adobe
Scaled Rollout and Adoption | Facilitating and supporting deliverables | Change Management Dashboard | Track adoption metrics, stakeholder engagement, and training completion | CX Partner - Change Management SME | 2025-12-01 | 2026-11-30 | Adobe
Implementation + Onboarding | Stakeholder Alignment Workshops | Stakeholder Map, Communication Strategy Draft | Ensure executive and stakeholder alignment before kickoff. | CX Partner - Change Management SME | 2025-12-01 | 2026-01-01 | Adobe
Scaled Rollout and Adoption | Change Readiness Assessment | Readiness Survey, Baseline Adoption Index | Assess cultural, technical, and operational readiness prior to implementation. | CX Partner - Change Management SME | 2025-12-01 | 2026-01-01 | Adobe
Implementation + Onboarding | Program management and coordination | Project Governance Tracker, Phase 1 Exit Report | Program coordination, kickoff, and phase review oversight | Project Manager | 2025-12-01 | 2026-11-30 | Knapsack
Implementation + Onboarding | Communication Launch Plan | Internal Communication Plan, Branding Package | Launch program messaging, goals, and brand identity across teams. | CX Partner - Change Management SME | 2025-12-01 | 2026-01-01 | Adobe
Implementation + Onboarding | Preparation | Technical Readiness Checklist | Verify infrastructure readiness, environment setup, and permissions | Project Manager | 2026-01-01 | 2026-02-01 | Knapsack
Implementation + Onboarding | Local install support | Installation Validation Report | Validate local environment setup for Knapsack and IPE components | Senior Solutions Engineer | 2026-01-01 | 2026-02-01 | Knapsack
Implementation + Onboarding | Component rendering | Rendering QA Report | Validate successful rendering of Spectrum components across environments | Senior Solutions Engineer | 2026-01-01 | 2026-02-01 | Knapsack
Implementation + Onboarding | SME support for rendering | Architecture Validation Log | SME oversight of rendering logic and architectural consistency | Subject Matter Expert | 2026-01-01 | 2026-02-01 | Knapsack
Implementation + Onboarding | Deployment support | Deployment Plan + Success Metrics | Plan and validate deployment pipelines with measurable success criteria | Senior Solutions Engineer | 2026-03-01 | 2026-07-01 | Knapsack
Scaled Rollout and Adoption | FDE led Implementation + Architecture + Governance | System of Systems Architecture Document | Define architecture, component contribution model, accessibility, governance framework | Senior Solutions Engineer | 2026-01-01 | 2026-03-01 | Knapsack
Scaled Rollout and Adoption | Stakeholder Interviews/Workshops | Strategic Readout and Recommendations | Collect stakeholder inputs and align roadmap | Senior Solutions Engineer | 2026-01-01 | 2026-03-01 | Knapsack
Scaled Rollout and Adoption | Pilot Enablement & Feedback Loop | Pilot Feedback Summary, Sentiment Dashboard | Gather early adopter feedback and adjust onboarding approach. | CX Partner - Change Management SME | 2026-03-01 | 2026-05-01 | Adobe
Scaled Rollout and Adoption | Role-Based Training Enablement | Persona-Based Training Modules (UX, Eng, Partner) | Deliver tailored enablement by persona to improve comprehension and adoption. | CX Partner - Change Management SME | 2026-06-01 | 2026-08-01 | Adobe
Scaled Rollout and Adoption | SME support for Deployment/DevOps | DevOps Readiness | Validate CI/CD, cloud authoring, and deployment automation readiness | Subject Matter Expert | 2026-01-01 | 2026-04-01 | Knapsack
Scaled Rollout and Adoption | Cloud authoring setup and testing | Cloud Authoring Validation | Setup and validate authoring in cloud environments | Senior Solutions Engineer | 2026-05-01 | 2026-06-01 | Knapsack
Scaled Rollout and Adoption | SSO setup and testing | SSO Integration Checklist | Configure and test single sign-on with enterprise identity provider | Subject Matter Expert | 2026-05-01 | 2026-06-01 | Knapsack
Scaled Rollout and Adoption | Training - Eng / UX / Partners | Unified Enablement Curriculum | Integrated training for engineering, UX, and partner audiences | Senior Solutions Engineer | 2026-07-01 | 2026-09-01 | Adobe
Scaled Rollout and Adoption | Workflow Diagrams | Workflow Documentation (FigJam, Token Studio, Contribution Workflows) | Map self-service contribution and implementation workflows | Senior Solutions Engineer | 2026-02-01 | 2026-03-01 | Knapsack
Scaled Rollout and Adoption | Content planning and integration | Multi-platform Implementation Guides | Documentation for web, React, iOS, Android implementations | Senior Solutions Engineer | 2026-05-01 | 2026-07-01 | Knapsack
Scaled Rollout and Adoption | Advanced Training - Partners + Contribution | Advanced Enablement Program | Deep-dive enablement for partner contributions | Senior Solutions Engineer | 2026-07-01 | 2026-09-01 | Adobe
Scaled Rollout and Adoption | Phase Gate Strategic Recommendations + Documentation | Scaled Rollout Readiness Review | Formal phase gate review and recommendations | Senior Solutions Engineer | 2025-12-01 | 2026-11-01 | Knapsack
Scaled Rollout and Adoption | Pre-Cutover Readiness Review | Cutover Readiness Checklist, Technical Validation Sign-off, Risk Mitigation Plan | Validate all technical, operational, and training prerequisites; confirm SSO, component rendering, deployment readiness before final rollout. | Senior Solutions Engineer | 2026-06-01 | 2026-07-01 | Knapsack
Scaled Rollout and Adoption | Data & Configuration Freeze | Configuration Freeze Log, Environment Snapshot | Lock configuration and repositories; capture environment snapshot for rollback if needed before go-live. | Senior Solutions Engineer | 2026-06-01 | 2026-07-01 | Knapsack
Scaled Rollout and Adoption | Final UAT & Stakeholder Acceptance | UAT Sign-off Report, Known Issues Log | Conduct final user acceptance testing with pilot teams; log and triage known issues before launch. | Senior Solutions Engineer | 2026-06-01 | 2026-07-01 | Knapsack
Scaled Rollout and Adoption | Change Impact Analysis | Change Impact Log, Stakeholder Action Plan | Evaluate and manage business unit impacts during scale-up. | CX Partner - Change Management SME | 2026-01-01 | 2026-02-01 | Knapsack
Scaled Rollout and Adoption | Adoption Acceleration Campaign | Awareness Campaign, Success Story Series | Promote awareness and highlight early success stories to drive adoption. | CX Partner - Change Management SME | 2026-11-01 | 2027-01-01 | Adobe
Scaled Rollout and Adoption | Partner Enablement & Recognition | Partner Contribution Leaderboard, Recognition Plan | Drive engagement through recognition and contribution metrics. | CX Partner - Change Management SME | 2026-09-01 | 2026-11-01 | Adobe
Optimization and Continued Support | Transition support | Continuous Improvement Plan | Continuous improvement plan with analytics and recommendations | Senior Solutions Engineer | 2026-06-01 | 2026-07-01 | Knapsack
Optimization and Continued Support | Cutover Execution | Deployment Completion Report, Access Validation, Service Health Dashboard | Execute production deployment; validate access controls, deployment integrity, and service health. | Senior Solutions Engineer | 2026-05-01 | 2026-06-01 | Knapsack
Optimization and Continued Support | Go-Live Communication Launch | Internal Announcement, Go-Live FAQ, Support Channels | Announce official go-live to stakeholders; provide communication templates and support channels. | Project Manager | 2026-06-01 | 2026-07-01 | Adobe
Optimization and Continued Support | Hypercare Phase (Post-Go-Live Support) | Hypercare Status Reports, Issue Resolution Tracker | Provide high-touch support for 30–90 days post go-live, track SLAs, and stabilize the system. | Senior Solutions Engineer | 2026-11-01 | 2027-02-01 | Knapsack
Optimization and Continued Support | Post-Implementation Review | Lessons Learned Summary, KPI Report, Optimization Backlog | Evaluate performance, adoption, and partner satisfaction to inform optimization roadmap. | Project Manager | 2026-12-01 | 2026-12-01 | Adobe
Optimization and Continued Support | Transition to Steady-State Operations | Knowledge Transfer Documentation, Ownership Matrix, Future Roadmap | Transition ownership to internal design ops and engineering teams; confirm governance cadence. | Design System Lead | 2026-12-01 | 2026-12-01 | Adobe
Optimization and Continued Support | Continuous Improvement Framework | Adoption Dashboards, Sentiment Trend Reports | Maintain engagement and track long-term adoption trends. | CX Partner - Change Management SME | 2026-06-01 | 2026-07-01 | Adobe
Optimization and Continued Support | Strategic Partnership Review | Quarterly Business Review Deck | Evaluate ongoing partnership alignment and strategic direction. | CX Partner - Change Management SME | 2026-11-01 | 2027-11-01 | Knapsack
Optimization and Continued Support | Case Study Development | Internal Case Study + Success Metrics | Document program success and outcomes for future scaling. | CX Partner - Change Management SME | 2026-11-01 | 2026-12-01 | Adobe

## Assumptions
Assumption | Value | Notes
Hours per Day | 8 | Used when Effort Type = Days
Hours per Week | 35.5 | Used when Effort Type = FTE
Default Weeks for FTE lines | 4 | Change per line in Plan if needed
Scenario Settings
Selected Scenario | Medium
Scenario | Hour Multiplier | Rate Multiplier | Contingency %
Low | 0.9 | 0.98 | 0.05
Medium | 1 | 1 | 0.1
High | 1.1 | 1.03 | 0.2

## Lookups - Rates
Vendor | Role | Rate Type | Hourly Rate | Daily Rate | Notes | VendorList | RolesList | Key_VendorRole
Knapsack | Project Manager | Hourly | 180 |  |  | Adobe
Knapsack | Senior Solutions Engineer | Hourly | 220 |  |  | Knapsack
Knapsack | Subject Matter Expert | Hourly | 500
Knapsack | CX Partner - Change Management SME | Hourly | 300
Knapsack | Product Engineer | Hourly | 400

## Lookups - Complexity
Phase | Milestone Activties | Low (hrs) | Medium (hrs) | High (hrs) | Key
Implementation + Onboarding | Program management and Steering Committee coordination | 104 | 120 | 140
Scaled Rollout and Adoption | Facilitating and supporting deliverables | 20 | 40 | 60
Implementation + Onboarding | Stakeholder Alignment Workshops | 12 | 18 | 28
Implementation + Onboarding | Change Readiness Assessment | 6 | 8 | 16
Implementation + Onboarding | Program management and coordination | 20 | 40 | 70
Implementation + Onboarding | Communication Launch Plan | 6 | 8 | 16
Implementation + Onboarding | Preparation | 4 | 8 | 14
Implementation + Onboarding | Local install support | 8 | 16 | 28
Implementation + Onboarding | Component rendering | 8 | 16 | 28
Implementation + Onboarding | SME support for rendering | 12 | 18 | 28
Implementation + Onboarding | Deployment support | 4 | 8 | 14
Implementation + Onboarding | FDE led Implementation + Architecture + Governance | 400 | 600 | 800
Implementation + Onboarding | Stakeholder Interviews/Workshops | 20 | 30 | 45
Scaled Rollout and Adoption | Pilot Enablement & Feedback Loop | 4 | 6 | 9
Scaled Rollout and Adoption | Role-Based Training Enablement | 8 | 16 | 28
Scaled Rollout and Adoption | SME support for Deployment/DevOps | 8 | 18 | 28
Scaled Rollout and Adoption | Cloud authoring setup and testing | 8 | 16 | 28
Scaled Rollout and Adoption | SSO setup and testing | 4 | 8 | 16
Scaled Rollout and Adoption | Training - Eng / UX / Partners | 8 | 16 | 28
Scaled Rollout and Adoption | Workflow Diagrams | 8 | 16 | 28
Scaled Rollout and Adoption | Content planning and integration | 20 | 30 | 45
Scaled Rollout and Adoption | Advanced Training - Partners + Contribution | 6 | 8 | 16
Scaled Rollout and Adoption | Phase Gate Strategic Recommendations + Documentation | 4 | 6 | 9
Scaled Rollout and Adoption | Pre-Cutover Readiness Review | 4 | 6 | 9
Scaled Rollout and Adoption | Data & Configuration Freeze | 4 | 6 | 9
Scaled Rollout and Adoption | Final UAT & Stakeholder Acceptance | 8 | 16 | 28
Scaled Rollout and Adoption | Change Impact Analysis | 4 | 6 | 9
Scaled Rollout and Adoption | Adoption Acceleration Campaign | 8 | 16 | 28
Scaled Rollout and Adoption | Partner Enablement & Recognition | 8 | 16 | 28
Optimization and Continued Support | Transition support | 12 | 18 | 28
Optimization and Continued Support | Cutover Execution | 8 | 16 | 28
Optimization and Continued Support | Go-Live Communication Launch | 8 | 16 | 28
Optimization and Continued Support | Hypercare Phase (Post-Go-Live Support) | 45 | 50 | 55
Optimization and Continued Support | Post-Implementation Review | 4 | 6 | 9
Optimization and Continued Support | Transition to Steady-State Operations | 8 | 16 | 28
Optimization and Continued Support | Continuous Improvement Framework | 8 | 16 | 28
Optimization and Continued Support | Strategic Partnership Review | 2 | 4 | 8
Optimization and Continued Support | Case Study Development | 8 | 16 | 28
Implementation + Onboarding | Design System Charter & Reference Architecture | 16 | 28 | 45
Implementation + Onboarding | Foundations & Token Taxonomy | 24 | 40 | 60
Implementation + Onboarding | Token Pipeline Build & Theming Strategy | 32 | 56 | 90
Implementation + Onboarding | Component Inventory & Prioritization | 16 | 24 | 36
Implementation + Onboarding | Component API Standards & Templates | 24 | 40 | 60
Implementation + Onboarding | Code Connect Strategy & Configuration | 24 | 40 | 70
Implementation + Onboarding | Documentation IA & Templates (Design System Docs) | 16 | 28 | 45
Implementation + Onboarding | Quality Gates Setup (A11y, Visual, Performance, Security) | 24 | 44 | 70
Implementation + Onboarding | Release Engineering & Package Strategy | 24 | 44 | 70
Implementation + Onboarding | AI Contextual Capabilities – Context Model & Knowledge Base | 32 | 60 | 120
Scaled Rollout and Adoption | Component Library MVP Build (Core Set) | 60 | 120 | 220
Scaled Rollout and Adoption | Code Connect Coverage Expansion & Drift Remediation | 32 | 60 | 120
Scaled Rollout and Adoption | Docs Launch + Recipes & Migration Guides | 24 | 44 | 70
Scaled Rollout and Adoption | Partner Contribution Pathway & Certification | 24 | 44 | 70
Scaled Rollout and Adoption | AI Contextual Capabilities – Workflow Integrations | 40 | 80 | 160
Scaled Rollout and Adoption | AI Contextual Capabilities – Evaluation Harness + Telemetry | 32 | 64 | 120
Optimization and Continued Support | Continuous Quality & Accessibility Automation | 24 | 44 | 70
Optimization and Continued Support | Release Cadence, Deprecations & Migrations | 24 | 44 | 70
Optimization and Continued Support | Adoption Analytics & Reporting (Design↔Code) | 16 | 28 | 45
Optimization and Continued Support | AI Contextual Capabilities – Guardrails, Governance & Iteration | 24 | 50 | 100
Optimization and Continued Support | AI Contextual Capabilities – Feedback Loop + Knowledge Refresh | 16 | 30 | 60

## PCRI Assessment
Product System Readiness Index (PCRI) Assessment
PCRI Version | 1.2 |  | Assessment Type | Baseline
System Landscape | Single |  | Is Multi-System?
Scoring scale | 0-10 (0 none; 10 best-in-class) |  | Last Updated
Pillar | Question ID | Question | Weight | Response (0–10) | Weighted Points | Max Points | PCRI Outputs
Foundation | F1 | Design system state (tokens/components/docs) | 1.5 | 5
Foundation | F2 | Token architecture maturity (semantic layering, theming) | 2 | 5 |  |  | Foundation (raw)
Foundation | F3 | Documentation quality + discoverability | 1 | 5 |  |  | AI Readiness (raw)
Foundation | F4 | Accessibility standards + enforcement | 1.5 | 5 |  |  | Governance (raw)
AI Readiness | AI1 | AI tool usage in design/dev workflows | 1.5 | 5 |  |  | Delivery (raw)
AI Readiness | AI2 | API maturity + component interface consistency | 2 | 5 |  |  | Culture (raw)
AI Readiness | AI3 | Product/design data quality + access | 1.5 | 5 |  |  | AI Gate Applied?
AI Readiness | AI4 | AI governance (context, safety, evaluation) | 2 | 5 |  |  | Delivery Gate Applied?
Governance | G1 | Executive sponsor + decision rights clarity | 2 | 5 |  |  | Foundation (effective)
Governance | G2 | Budget commitment + capacity allocation | 1.5 | 5 |  |  | AI Readiness (effective)
Governance | G3 | Change capacity + comms operating cadence | 1 | 5 |  |  | Governance (effective)
Governance | G4 | ROI measurement + KPI instrumentation | 1.5 | 5 |  |  | Delivery (effective)
Governance | G5 | Cross-functional governance structure (design/eng/product) | 1.5 | 5 |  |  | Culture (effective)
Delivery | D1 | Decision clarity in delivery workflow | 1 | 5 |  |  | PCRI Score
Delivery | D2 | Experiment pace + iteration loops | 1.5 | 5 |  |  | Archetype
Delivery | D3 | Cross-functional collaboration consistency | 1 | 5 |  |  | Multi-System Score
Delivery | D4 | Toolchain integration (design↔code, CI/CD, docs) | 1 | 5
Delivery | D5 | Workflow consistency across teams/products | 1.5 | 5
Delivery | D6 | Platform team model / enablement pathways | 1.5 | 5
Delivery | D7 | Deployment frequency + release discipline | 1.5 | 5
Culture | C1 | Contribution model exists and is used | 1.5 | 5
Culture | C2 | Contributor diversity across org | 1 | 5
Culture | C3 | Community health (cadence, engagement) | 1 | 5
Culture | C4 | Shared ownership (design+engineering) | 1.5 | 5
Culture | C5 | Time allocation for contribution | 1 | 5
Culture | C6 | Psychological safety | 2 | 5
Culture | C7 | Information flow (Westrum typology indicator) | 1.5 | 5
Multi-System Architecture (optional)
Shown when System Landscape ≠ Single. Does not affect core PCRI.
Pillar | Question ID | Question | Weight | Response (0–10) | Weighted Points | Max Points
Multi-System | MS27 | Token architecture across systems (semantic vs primitive layers) | 1.5 | 5
Multi-System | MS28 | Component abstraction across systems | 1.5 | 5
Multi-System | MS29 | Cross-system governance + decision rights | 2 | 5
Multi-System | MS30 | Cross-system AI context unification | 1.5 | 5
Multi-System | MS31 | Cross-system contribution model | 1.5 | 5
Multi-System | MS32 | Release coordination across systems | 1 | 5

## PCRI WBS Mapping
Phase | Activity / Milestone | Activity Key | Primary PCRI Pillar | Builder (1/0) | Adopter (1/0) | Optimizer (1/0) | Transformer (1/0) | Pillar Threshold Override (optional) | Pillar Score (eff) | Archetype | Include? | PCRI Mult
Implementation + Onboarding | Stakeholder Alignment Workshops |  | Delivery | 1 | 1 | 1 | 1
Implementation + Onboarding | Program management and coordination |  | Delivery | 1 | 1 | 1 | 1
Implementation + Onboarding | Communication Launch Plan |  | Delivery | 1 | 1 | 1 | 1
Implementation + Onboarding | Preparation |  | Delivery | 1 | 1 | 1 | 1
Implementation + Onboarding | Local install support |  | Delivery | 1 | 1 | 1 | 1
Implementation + Onboarding | Component rendering |  | Foundation | 1 | 1 | 1 | 1
Implementation + Onboarding | SME support for rendering |  | Delivery | 1 | 1 | 1 | 1
Implementation + Onboarding | Deployment support |  | Delivery | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | Program management and Steering Committee coordination |  | Governance | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | Facilitating and supporting deliverables |  | Delivery | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | Change Readiness Assessment |  | Culture | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | FDE led Implementation + Architecture + Governance |  | Governance | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | Stakeholder Interviews/Workshops |  | Delivery | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | Pilot Enablement & Feedback Loop |  | Culture | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | Role-Based Training Enablement |  | Culture | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | SME support for Deployment/DevOps |  | Delivery | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | Cloud authoring setup and testing |  | Delivery | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | SSO setup and testing |  | Delivery | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | Training - Eng / UX / Partners |  | Culture | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | Workflow Diagrams |  | Delivery | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | Content planning and integration |  | Foundation | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | Advanced Training - Partners + Contribution |  | Culture | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | Phase Gate Strategic Recommendations + Documentation |  | Foundation | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | Pre-Cutover Readiness Review |  | Delivery | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | Data & Configuration Freeze |  | Delivery | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | Final UAT & Stakeholder Acceptance |  | Delivery | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | Change Impact Analysis |  | Culture | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | Adoption Acceleration Campaign |  | Delivery | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | Partner Enablement & Recognition |  | Culture | 1 | 1 | 1 | 1
Optimization and Continued Support | Transition support |  | Delivery | 1 | 1 | 1 | 1
Optimization and Continued Support | Cutover Execution |  | Delivery | 1 | 1 | 1 | 1
Optimization and Continued Support | Go-Live Communication Launch |  | Delivery | 1 | 1 | 1 | 1
Optimization and Continued Support | Hypercare Phase (Post-Go-Live Support) |  | Delivery | 1 | 1 | 1 | 1
Optimization and Continued Support | Post-Implementation Review |  | Delivery | 1 | 1 | 1 | 1
Optimization and Continued Support | Transition to Steady-State Operations |  | Delivery | 1 | 1 | 1 | 1
Optimization and Continued Support | Continuous Improvement Framework |  | Delivery | 1 | 1 | 1 | 1
Optimization and Continued Support | Strategic Partnership Review |  | Delivery | 1 | 1 | 1 | 1
Optimization and Continued Support | Case Study Development |  | Delivery | 1 | 1 | 1 | 1
Implementation + Onboarding | Design System Charter & Reference Architecture |  | Delivery | 1 | 1 | 1 | 1
Implementation + Onboarding | Foundations & Token Taxonomy |  | Foundation | 1 | 1 | 1 | 1
Implementation + Onboarding | Token Pipeline Build & Theming Strategy |  | Foundation | 1 | 1 | 1 | 1
Implementation + Onboarding | Component Inventory & Prioritization |  | Foundation | 1 | 1 | 1 | 1
Implementation + Onboarding | Component API Standards & Templates |  | Foundation | 1 | 1 | 1 | 1
Implementation + Onboarding | Code Connect Strategy & Configuration |  | AI Readiness | 0 | 1 | 1 | 1
Implementation + Onboarding | Documentation IA & Templates (Design System Docs) |  | Foundation | 1 | 1 | 1 | 1
Implementation + Onboarding | Quality Gates Setup (A11y, Visual, Performance, Security) |  | Delivery | 1 | 1 | 1 | 1
Implementation + Onboarding | Release Engineering & Package Strategy |  | Delivery | 1 | 1 | 1 | 1
Implementation + Onboarding | AI Contextual Capabilities – Context Model & Knowledge Base |  | AI Readiness | 0 | 0 | 1 | 1 | 70
Scaled Rollout and Adoption | Component Library MVP Build (Core Set) |  | Foundation | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | Code Connect Coverage Expansion & Drift Remediation |  | AI Readiness | 0 | 1 | 1 | 1
Scaled Rollout and Adoption | Docs Launch + Recipes & Migration Guides |  | Foundation | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | Partner Contribution Pathway & Certification |  | Delivery | 1 | 1 | 1 | 1
Scaled Rollout and Adoption | AI Contextual Capabilities – Workflow Integrations |  | AI Readiness | 0 | 0 | 1 | 1 | 70
Scaled Rollout and Adoption | AI Contextual Capabilities – Evaluation Harness + Telemetry |  | AI Readiness | 0 | 0 | 1 | 1 | 70
Optimization and Continued Support | Continuous Quality & Accessibility Automation |  | Delivery | 0 | 1 | 1 | 1
Optimization and Continued Support | Release Cadence, Deprecations & Migrations |  | Delivery | 0 | 1 | 1 | 1
Optimization and Continued Support | Adoption Analytics & Reporting (Design↔Code) |  | Delivery | 0 | 1 | 1 | 1
Optimization and Continued Support | AI Contextual Capabilities – Guardrails, Governance & Iteration |  | AI Readiness | 0 | 0 | 1 | 1 | 70
Optimization and Continued Support | AI Contextual Capabilities – Feedback Loop + Knowledge Refresh |  | AI Readiness | 0 | 0 | 1 | 1 | 70